| Management & System |
| --- |
| Meetings |  |
| 05/07 | FSE internal meeting, coordination , needed FSE to be studied & developed |
| 12/07 | SPIRE Grounding Telecon |
| 15/07 | SPIRE Grounding Telecon |
| 18/07 | SPIRE Grounding Telecon |
| Management act. |  |
| Project control | SPIRE master schedule updated. DCU EM QM1 detailed schedule. SPIRE FPU simulator detailed schedule update. Action list update. SPIRE reporting. |
| DRCU/DDR | Documentation sent on July 2nd |
| SAp / JPL | F. Pinsard stay at Caltech : 11/04 to 10/06: DAQ IF + board test 24/06 to 12/07: BIAS board test 29/07 to 15/08: LIA-P 02/09 to 08/10: LIA-S test board + functional system test + performance system test |
| Cooler harness procurement | STM & CQM cooler harness will be procured via Tekdata. Order will be placed as soon as Specification will be available from RAL. |
| Team | Françoise Loubère moved to a private company. Philippe Lavocat will take over the QA management responsibilities until a new QA responsible would be appointed. |
| 2. Problem Areas | Remedial Actions |
| Lack of agreement on the Grounding scheme approach could impact both DRCU design and delay. | A dedicated review is going to be held in September. |
| Potential risk on DRCU FM delivery: Grounding scheme issue prevents (among else) to send out the PSU call for tender. | See DRCU workpackage section. |
| 1 month delay on QM1 delivery mainly due to DCU development schedule slippage. | None. Minor issue compared to the grounding scheme one. |
| 3. Actions |
| Still Opened |  |
| Ref. | Meeting | Actionnee | Due date | Action |
| / | / | / | / | / |
| Closed |  |
| Ref. | Meeting | Actionnee | Due date | Action |
| / | / | / | / | / |
| 4. Project Milestones |
| Main Delivery Milestones | Resp. | Baseline | Current |
| DRCU QM1 delivery to RAL | SAp | 03/03/2003 | 04/04/03 |
| FPU Simulator (version 1) delivery to RAL | SAp | 03/03/2003 | 04/04/03 |
| DRCU QM2 delivery to RAL | SAp | 05/01/2004 | 05/01/2004 |
| DRCU FM delivery to RAL | SAp | 30/07/2004 | 30/07/2004 |

| DRCU |
| --- |
| DCU/QM1 | Status |
|  | DAQ IF 2 test boards available at JPL Test completed. BIAS Board assembly achieved 29/05 Board test performed LIA-P PCB fabrication achieved LIA-S PCB fabrication achieve Back-Planes Functional test backplane built. Test plan Test plans: LIA-P, LIA-S, BIAS, DAQ-IF available in draft form. Functional test plan: writing in progress. |
|  | Progress of the month |  |
|  | DAQ+IF test completed BIAS board test performed |
| SCU/QM1 | Status |
|  | Heaters: prototype test achieved. Temperature sensors: test successful DPU I/F command and data I/F achieved. Analog port study achievement, software primitive study in progress. Test board analog port study in progress. SCU Documentation Draft Specification and preliminary (H/W & VHDL) design available. Draft DPU/SCU ICD issued. Test plan writing in progress Functions Heater & temperature: implementation achieved Calibrator: implementation achieved. HSK: prototype board in fabrication, 2 people were added for a few month’s to study it, the test software and a FPGA to convert different communication protocols. SCU logic (pinout): study achieved SCU logic (logic): study in finalisation Boards Temperature: design PCB achieved. PCB layout in finalisation. Cchkif: design PCB achieved. Board scheme finalisation. Back plane: design PCB in finalisation. |
|  | Progress of the month |  |
|  | HSK function study SCU logic function study finalisation QM1 back plane scheme finalisation QM1 temperature board scheme achievement, PCB layout finalisation QM1 CCHKiF board scheme finalisation Analog port software primitive Test board analog port Test plan writing |
| MCU I/F | Status |
|  | Design available at LAM & SAp MCU QM1 delivery to SAp confirmed 12/12/2002. |
|  | Progress of the month |  |
|  | Work in progress |
| PSU | Status |
|  | Separated power bench will be used for QM1 and QM2. Draft Specification available. Call for tender process stuck Contractual specification writing stuck Wait for S/C I/F to continue…See problem area. |
|  | Progress of the month |  |
|  | Little because of lack of I/F specification (grounding scheme). |
| DRCU Boxes | Status |
|  | Modeling completed. DCU board front panel design achieved DCU Box. STM: detailed design achieved, fabrication in progress. QM1: detailed design update achieved, fabrication in progress QM2 & FM: I/F available. FCU Box. STM: detailed design achieved, ready for fabrication. QM1: detailed design achieved, fabrication in progress. Thermal & dynamic studies in progress QM2 & FM: I/F available |
|  | Progress of the month |  |
|  | DCU STM fabrication started. DCU QM1 & FCU QM1 box fabrication started FCU box thermal & dynamic studies. |

| Test Equipments & others |
| --- |
| LTU #1 | Status |
|  | Specifications: available (see documentation). Hardware & software architecture definition: near to completion. Software development: in progress. Software procurement: in progress Hardware procurement: in progress. Power bench: specification writing in progress. |
|  | Progress of the month |  |
|  | Software procurement (call for tender…) Soft development. |
| FPU Simulator #1 | Status |
|  | Specification available Electronics prototyping ongoing S/W evaluation on going Rack study in progress. PXI TRIG IO Hardware test achieved. Second fabrication achieved. VHDL update achieved. PXI BOLO SPIRE Electronic & design Achieved. VHDL soft studies. Test software specification writing achieved. Test board configuration study & realisation achieved. Functional test achieved. PXI heater/Supply Design achieved. Manufacturing file ritten. Test software specifications achieved. Test board configuration study & realization achieved. Onboard VHDL software study achieved. PXI part fabrication started week 21 (sub-contractor SPCI & ERTE). PXI Cernox DC & AC Analogue studies & design achieved. Complementary tests achieved. Manufacturing file writing achieved, Test software specifications achieved. Test board configuration study & realisation achieved. Onboard VHDL software study over at 50%. PXI part fabrication started week 21 (sub-contractor SPCI & ERTE). Software Supervision software specification writing. Output & input file configuration specification writing. PXI BOLO SPIRE, PXI HEATER / SUPPLY, PXI CERNOX, PXI TRIGGER IO test software development achieved. |
|  | Progress of the month |  |
|  | No progress report available due to vacation period. |

| Part procurement | Status |
| --- | --- |
|  | Declared components list update: edition 13 OP400 qualification review 12/02/02. Fabrication started. Harnesses connector estimation carried out. ATP update with Technologica |
|  | Progress of the month |  |
|  | Components reception QM ATP updating FM ATP updating New ATP : connectors |
| Harness | Status |
|  | Test Harness configuration scheme available Connectors procurement on going |
|  | Progress of the month |  |
|  | DCU harness configuration done after many e-mail were send between SAp & JPL about configuration. Contact with the manufacturer who will make a price offer. |
| Containers | Status |
|  | Specification available. |
|  | Progress of the month |  |
|  | None |
| AIV | Status |
|  | DRCU development tree available (last version 30/11/2001) Board Test plan writing in progress. DRCU AIV plan in progress. |
|  | Progress of the month |  |
|  | DRCU AIV plan writing. |
| PA/QA | Status |
|  | DML and DPL draft available. Reference documentation list update on going |
|  | Progress of the month |  |
|  | Updating of the reference document list. Building of Requirement Cross verification table. Non conformity managment |

| Problem Areas | Remedial Actions |
| --- | --- |
| Test Harnesses: detailed definition not yet available. Harness procurement could be on the critical path on the short term. | Priority will be defined. |
| Milestones | Status |
| DCU EM QM1 delivery to SAp from JPL | 06/11/2002 | Delayed by 1 month |
| DRCU QM1 harnesses need date | 06/11/2002 | On schedule |
| LTU DRCU need date | 06/11/2002 | On schedule |
| SPIRE FPU simulator #1 need date delivery to SAp | 06/11/2002 | Delayed by 1 month |
| Detector test cryostat delivery to SAp by JPL | 25/11/2002 | On schedule |
| MCU QM1 + simulator need date delivery to SAp | 10/12/2002 | On schedule |
| SCU QM1 delivery by SEDI need date | 24/12/2002 | On schedule |
| DRCU QM1 delivery to RAL | 03/03/2003 | Delayed by 1 month |
| SPIRE FPU simulator #2 need date | 28/07/2003 | On schedule |
| SCU QM2 need date | 27/08/2003 | On schedule |
| MCU QM2 delivery to SAp need date | 27/08/2003 | On schedule |
| DRCU QM2 delivery to RAL | 05/01/2004 | On schedule |
| MCU FM delivery to SAp need date | 26/04/2004 | On schedule |
| SCU FM need date | 05/05/2004 | On schedule |
| DRCU FM ready for delivery to RAL | 30/07/2004 | On schedule |

| Documentation progress this month |
| --- |
| Title | Reference | Progress |
| None this month |  |  |

| Documentation List |
| --- |
| Title | Reference | Version, date |
| Reference documentation |
| SPIRE Instrument Development Plan IIDR | / | Issue 1.1 12/4/2001 IIDR |
| SPIRE Major Milestone List issue 1.3 IIDR | SPIRE-RAL-PRJ-000455 | Issue 1.3 |
| SPIRE Instrument Requirements | 34 | Issue 1.0 23/11/00 |
| SPIRE System Budget | / | Issue 3.4 24/07/2001 |
| Cryo-cooler Control Specification | / | / |
| Calibrator SSSD: SCAL Calibrator SSSD : PCAL | HSO-CDF-SP-001 HSO-CDF-SP-003 | Issue 1.0 10/9/2001 Issue 1.0 11/9/2001 |
| Detector SSSD | / | Issue 3.1 – draft |
| Shutter SSSD | Not yet | / |
| Instrument Interface Document part A | SCI-PT-IIDA-04624 | 3.0 01/07/2002 |
| Instrument Interface Document part B SPIRE | SCI-PT-IIDB/SPIRE-02124 | 2.0, 31/07/2001 |
| SPIRE configurable document tree | SPIRE-RAL-PRJ-00033 | 3.1 03/05/2001 |
| SPIRE product tree | SPIRE-RAL-PRJ-00455 | 1.0 09/11/1999 |
| SPIRE instrument development plan | SPIRE-RAL-PRJ-0035 | 1.0 20/05/2000 |
| SPIRE management plan | SPIRE-RAL-PRJ-00029 | 01/01/2001 |
| SPIRE Data ICD | SPIRE-RAL-DOC-001078 | 1.0 draft1 15/01/2002 |
| SPIRE instrument AIV plan | SPIRE-RAL-PRJ-000410 | 2.1 29/03/2001 |
| Management |
| Management plan for the Herschel project. | SAp-FIRST-JLA-0038-01 | 3.0 23/11/2001 |
| Actions list | SAp-FIRST-DR-0050-01 |  |
| DRCU & WIH Development Plan | SAp-SPIRE-JLA-0047-01 | 3.0 27/11/2001 |
| SPIRE product tree | SAp-FIRST-DR-0071-02 | 1.2 |
| WBS Herschel | SAP-FIRST-DR-0043-01 | 2.1 |
| WBS SPIRE | SAP-FIRST-DR-0045-01 | 2.1 |
| SPIRE master schedule | SAp-SPIRE-DR-0053-02 | 3.1 31/07/2002 |
| DCU EM QM1 at JPL detailed schedule | SAP-FIRST-DR-0050-01 | 4.6 31/07/2002 |
| SPIRE FPU simulator detailed schedule | SIG-FIRST-PdA-0052-01 | 12.0 31/07/2002 |
| SCU QM1 detailed schedule | SEI-SPIRE-MM-0049-01 | 1.0 31/07/2002 |
| LTU & power bench detailed schedule | SAp-FIRST-DR-0069-02 | 2.7 31/07/2002 |
| DRCU |
| DRCU Specifications document | SAp-SPIRE-Cca-0025-00 | Issue 0.92 26/06/2002 |
| DRCU Development Tree | H0030 | 30/11/2001 |
| DRCU ICD | SAp-SPIRE-Cca-0075-02 | 0.7 26/06/2002 |
| DRCU DPU ICD | SAp-SPIRE-Cca-0076-02 | 0.7 26/06/2002 |
| DCU design document | SAp-SPIRE-FP-0063-02 | 0.2 05/07/2002 |
| Test plan DAQ IF | SAp-SPIRE-FP-0067-02 | 0.1 draft |
| Test plan BIAS | SAp-SPIRE-FP-0066-02 | 0.1 draft |
| Test plan LIA P | SAp-SPIRE-FP-0064-02 | 0.1 draft |
| Test plan LIA S | SAp-SPIRE-FP-0065-02 | 0.1 draft |
| SPIRE test configuration, | SAp-SPIRE-LD-0015-01 | 3.0 08/2001 |
| FPU simulator specifications for DCU / SCU test | SIG-SPIRE-PdA-0030-01 | 19/03/2001 |
| SPIRE LTU specifications | SAp-SPIRE-FD-0071-02 | 1.0 22/04/2002 |
| QA |
| Standard product assurance plan | SAp-GERES-Flo-436-00 | 1.0 09/11/2000 |
| SPIRE liste des documents à produire | SAp-SPIRE-Flo-0028-00 | 0.2 15/12/2000 |
| Organisation de la gestion documentaire sur Herschel au SAp | SAp-FIRST-DR-0053-01 | 1.1 06/12/2001 |
| Gestion des documents sur la base Herschel | SAp-FIRST-DR-0072-02 | 1.3 15/04/2002 |
| Procédures de contrôle projet sur Herschel | SAp-FIRST-DR-0125-02 | 1.2 13/05/2002 |
| DRCU FMECA Report |  | Issue 1.0 25/10/2001 |
| Analyse de fiabilité du DRCU | SAp-SPIRE-Flo-0039-01 | 21/08/2001 |
| DRCU processor board product assurance specification | SAp-SPIRE-Flo-0020-00 | 10/01/2001 |
| Plan d’action de l’Assurance Produit du projet Herschel | SAp-FIRST-Abx-0137-02 | Issue 1.1 18/06/2002 |