Work Package:	Structure                                                             SPIRE-MSS-REP-001415

| 1. Subsystem Progress Since Project Inception |
| --- |
| Several concepts evaluated for the structure. Base line design decided upon in June 2000. Working on the system implications and implementation since first half of 2001. Continuing to close interfaces with the various subsystems. Started with production drawings in February 2001. The concept of the suspension has been analysed and decided on implementation. Hardware produced and tested, meets specifications. Detailed design continuing and manufacture is continuing. |
| 2. Subsystem Progress This Month |
| Subsystem interfaces for RF filters and SMEC are frozen by the structure. Thermal busbar development has started. Production drawings are still in progress. Awaiting Cardiff to send MKIII units for testing so that the FEA can be completed in early September. MGSE production has been completed and awaiting HOB simulator before assembly – This is due mid September. Production of the photometer 2K box spine and covers is still continuing, though the cover walls have been completed. The manufacture of the light traps have been completed. The redesign of SCAL box is still being debated. Spectrometer 2K Detector box is still in manufacture. Optical Bench drawing has been released and is in manufacture. Main FPU mounts and detector box mounts have been released and are in manufacture. Continuing to have integration team meetings with RAL, to address planning and integration issues. Analysis reports completed. |
| 3. Problem Areas | Remedial Action |
| -Difficult to close interface definitions. Also other subsystems have problems with them. Thermal busbar suspension has strong non-linear responses Level 1 thermal strap interface with spacecraft still is not confirmed Problems within the SCAL baffle box, forseen by the Optical team (LAM and RAL), have led to some redesign of the SCAL BOX | -Most interfaces are closed. The outstanding ones include the RF filters, JFETS and the SMEC. MSSL has taken their interface to these items to be frozen. Development team has been set up to redefine design. Continuing to work to implement design without effecting the schedule. Have produced design for the thermal bus bar itself . Awaiting Cardiff to produce MKIII of its support in early September to finish testing and FEA work. Production design work will start on 24 September Design work on SCAL box completed and awaiting confirmation from LAM and RAL. |
| 4. Engineering Activities |
| Analysis and alignment reports continuing. FEA on thermal busbar. |
| 5. Design Changes |
| - |
| 6. PA/QA Activities |
| NCR raised on one of the one piece photometer cover walls – repair is in placed and NCR closed out on 29 August 2002 |
| 7. Subsystem Management Issues |
| - |
| 8. Actions Requiring Immediate Attention |
| - |
| 9. Status of Previous Actions |
| - |
| 10. Activities Yet to be Achieved |
| 11. Milestones | Status |
| February 2002 13-08-2002 01-02-2002 10-06-2003 01-10-2002 6-01-2004 | Interfaces defined and reported STM delivery to RAL CQM FTB enclosure to RAL PFM delivery to RAL PFM FTB enclosure to RAL FS delivery to RAL | On going On schedule – now 2 months late-15-10-02 On schedule On schedule On schedule |
| 13. Schedule Changes |
| Due to the thermal busbar design, manufacturing problems, and optical bench checking we are lagging 2.5 months behind on original schedule. |