Work Package:	BSM                                                                      SPIRE-ATC-REP-001441

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype tests complete. IBDR complete. Development Model testing |
| 2. Subsystem Progress This Month |
| STM ADP issued 27.Sep.02. DM-2 assembly commenced. Investigations on options to reduce cost of Zeiss/PACS motor coils complete. Mating connectors and test boxes for LAM electronics completed. |
| 3. Problem Areas | Remedial Action |
| Full checks on repeatability/linearity in dewar to be achieved Launch Latch relocated on design and problem noted with DM-2 motor wiring. Zeiss motor quotation above budget price. Wiring layout and specification TBC. Cash flow (esp. allocations vs Zeiss purchase orders) | high efficiency anti-reflection coating window received and tested warm. Will test further in conjunction with DM-2. Change to proposed ATC mounting in hand - will need to tie up with LAM. Will need to use fewer motor coils. Discussions with RAL (D.Griffin) scheduled. Discussions in hand with funding body |
| 4. Engineering Activities |
| STM assembly with ballast mass completed. Investigated problem on thermometry (change of calibration on bake-out to BSM specification). Cross calibration scheme (via beam splitter) for laser metrology completed. Software checkout prior to for |
| 5. Design Changes |
| Iterative assembly and balance check on DM-2 jiggle frame and wiring completed, and design modification introduced to trim balance. |
| 6. PA/QA Activities |
| Drawing configuration scheme is being run manually due to problems with database scheme - PA is being maintained but it is labour intensive and improvements to the data base are being sought. |
| 7. Subsystem Management Issues |
| Funding for motors. |
| 8. Actions Requiring Immediate Attention |
| SW11MAR02.02 IP Place contract for Zeiss motors … ongoing. Price received but > budget. |
| 9. Status of Previous Actions |
| IP/D.Griffin : ATC Need MSSL definition of harness run and back-shells to procure harness via RAL. … complete. Costs are higher than anticipated, but OK provided STM components are re-used for CQM, FSM. IP Configured Items Data List is required … issued as SPIRE-ATC-PRJ-00105 |
| 10. Activities Yet to be Achieved |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| 20K test dewar available | N/A | May.02 |  |  |
| Integrate Prototype (in place of DM 2) to LAM | 30 Mar 01 | Oct.02 |  | + 6 months |
| DM release for manufacture | Oct.01 | Nov.01 | Dec.01 |  |
| DM-2 release for manufacture | N/A | Apr.02 | Apr.02 |  |
| 2 axis prototyping at ATC complete | N/A | Mar.02 | Apr.02 |  |
| SPIRE IBDR | N/A | Mar.02 | Mar.02 |  |
| DM-2 tests complete | 30.Apr 02 | Oct.02 |  | + 4 weeks |
| BSM STM del'y to RAL | 01 Feb 00 | 10.Oct 02 |  | +6 weeks |
| BSM CQM delivery to LAM | Jul.02 | 20.Dec.02 |  | +8 weeks |
| BSM CQM del'y to RAL | 13 Mar 02 | Feb.03 |  | + 4 weeks |
| BSM QM tests complete (flight design valid) | 25.Apr.03 | 20.Jun.03 |  | +2 weeks |
| BSM PFM delivery to LAM | 03.Jun 03 | 04.Sep.03 |  | +2 weeks |