Work Package:	DPU                                                                        SPIRE-IFS-REP-001443

| 1. Subsystem Progress Since Project Inception |  |  |  |
| --- | --- | --- | --- |
| 2. Subsystem Progress This Month |  |  |  |
| After the ESA meeting on 19th of June and ESA statement to pay all CPPA components the ICC funding problem for years 2004-2006 looks to be relieved. We are still waiting for a formal ESA document in order to define activities with ASI about the available FM components money. - AVM OBS is next to completion. Items being implemented now are: - ability to generate up to 4 HK+Diag packets - ability to send packets and data from the VM - SVVP Issue 1.0 is being completed. It includes detailed test procedures and input specifications. - URD 1.1 is being updated following SPIRE comments |  |  |  |
| 3. Problem Areas |  |  | Remedial Action |
| 4. Engineering Activities |  |  |  |
| 5. Design Changes |  |  |  |
| 6. PA/QA Activities |  |  |  |
| 7. Subsystem Management Issues |  |  |  |
| 8. Actions Requiring Immediate Attention |  |  |  |
| None |  |  |  |
| 9. Status of Previous Actions |  |  |  |
| 10. Activities Yet to be Achieved |  |  |  |
| 11. Milestones |  | Status |  |
| 28/06/01 15/6/01 28/6/01 1/10/01 2/4/02 15/11/01 22/4/02 2/1/03 20/12/02 15/9/03 1/3/04 24/2/04 | DRCU simulator at IFSI CDMS (S/C I/F) at IFSI EGSE at IFSI DPU-AVM Board at IFSI DPU-AVM delivery to RAL QM author. To proceed DPU-QM Board at IFSI DPU-QM delivery to RAL FM author. To proceed DPU-FM Board at IFSI DPU-FM delivery to RAL FS ready for delivery | Late – expected completion 30/2/02 Late – Proto SW arrived on 21/8/01 Late – SCOS 2000 arrived on 20/8/01 Late – arrived on 15/04/02 Late – new date 1/07/02 Late - new date 15/02/02 On schedule On schedule On schedule On schedule On schedule On schedule |  |
| 13. Schedule Changes |  |  |  |
| None |  |  |  |