| Management & System |
| --- |
| Meetings |  |
| 04/09 | Internal DRCU AIV Plan review |
| 05/09 | Electronic and box design coordination |
| 20/09 | LTU progress and development plan |
| 23-24/09 | Grounding Scheme review at RAL |
| Management act. |  |
| Project control | SPIRE master schedule updated. DCU EM QM1 detailed schedule. SPIRE FPU simulator detailed schedule update. Action list update. SPIRE reporting. |
| SAp / JPL | F. Pinsard stay at Caltech : 11/04 to 10/06: DAQ IF + board test 24/06 to 12/07: BIAS board test 29/07 to 15/08: LIA-P 02/09 to 30/09: LIA-S test board + functional system test To be determined: integration, functional test, performances test |
| Cooler harness procurement | STM & CQM cooler harness procurement order placed to Tekdata |
| Problem Areas | Remedial Actions |
| Sorting out of the Grounding and EMI/EMC issue (outcome of the Grounding Scheme review) has delayed the finalisation of the PSU specification writing and the PSU call for tender accordingly. | FM will likely have to be powered by a powerbench as long as the PSU FM is not available. The PSU FM availability being on the critical path, the DRCU FM could be delayed. See DRCU workpackage section. |
| Actions |
| Still Opened |  |
| Ref. | Meeting | Actionnee | Due date | Action |
| / | / | / | / | / |
| Closed |  |
| Ref. | Meeting | Actionnee | Due date | Action |
| / | / | / | / | / |
| Project Milestones |
| Main Delivery Milestones | Resp. | Baseline | Current |
| DRCU QM1 delivery to RAL | SAp | 03/03/2003 | 24/04/03 |
| FPU Simulator (version 1) delivery to RAL | SAp | 03/03/2003 | 24/04/03 |
| DRCU QM2 delivery to RAL | SAp | 05/01/2004 | 05/01/2004 |
| DRCU FM delivery to RAL | SAp | 30/07/2004 | 30/07/2004 |

| DRCU |
| --- |
| DCU/QM1 | Status |
|  | DAQ IF 2 test boards available at JPL Test completed. BIAS Board assembly achieved 29/05 Board test performed LIA-P PCB fabrication achieved Board test performed LIA-S Board assembly achieved Board test performed Back-Planes Functional test backplane built. Performance test backplane design & PCB layout achieved Test plan Test plans: LIA-P, LIA-S, BIAS, DAQ-IF available in draft form. Functional test plan: writing in progress. Test Functional test achieved |
|  | Progress during the month |  |
|  | LIA-S board test achievement DAQ IF+BIAS+LIA-S+LIA-P functional test achieved Performance test backplane design & PCB layout achievement |
| SCU/QM1 | Status |
|  | Heaters: prototype test achieved. Temperature sensors: test successful DPU I/F command and data I/F achieved. Analog port study achievement, software preliminary study in progress. Test board analog port study in progress. SCU Documentation Draft Specification and preliminary (H/W & VHDL) design available. Draft DPU/SCU ICD issued. Test plan writing in progress Functions Heater & temperature: implementation achieved Calibrator: implementation achieved. HSK: prototype board in fabrication, 2 people were added for a few month’s to study it, the test software and a FPGA to convert different communication protocols. SCU logic (pinout): study achieved SCU logic (logic): study in finalisation Boards Temperature: design PCB achieved. PCB layout achieved. Cchkif: design PCB achieved. Board scheme finalisation. Back plane: PCB design & layout achieved. |
|  | Progress during the month |  |
|  | Backplane PCB layout achievement Temp board PCB layout achievement CCHKIF scheme finalisation Test board: analog port |
| MCU I/F | Status |
|  | Design available at LAM & SAp MCU QM1 delivery to SAp confirmed 12/12/2002. |
|  | Progress during the month |  |
|  | No report available from LAM |
| PSU | Status |
|  | Separate power bench will be used for QM1 and QM2 and FM. Draft Specification available. Call for tender process stuck Contractual specification writing stuck Wait for S/C I/F to continue…See problem area. |
|  | Progress during the month |  |
|  | None because of lack of I/F specification (grounding scheme). |
| DRCU Boxes | Status |
|  | Modeling completed. DCU STM board front panel design & fabrication achieved DCU STM rack fabrication in progress DCU Box. STM: detailed design achieved, fabrication in progress. QM1: available at SAp. QM2 & FM: I/F available. FCU Box. STM: detailed design achieved, ready for fabrication. QM1: Available at SAp. Thermal & dynamic studies in progress QM2 & FM: I/F available |
|  | Progress during the month |  |
|  | DCU STM box fabrication. DCU STM boards study and fabrication achievement DCU STM rack fabrication FCU box thermal & dynamic studies. DCU & FCU QM1 "light" boxes available. |

| Test Equipments & others |
| --- |
| LTU #1 | Status |
|  | Specifications: available (see documentation). Hardware & software architecture definition: achieved. Software development: in progress. Software procurement: development system delivered Hardware procurement: Industrial PC, boards delivered. |
|  | Progress during the month |  |
|  | Soft development. Soft procurement:OS, development system delivered Hardware procurement: Industrial PC, boards delivered |
| FPU Simulator #1 | Status |
|  | Specification available Electronics prototyping ongoing S/W evaluation on going Rack study in progress 80%. PXI TRIG IO Hardware test achieved. Second fabrication achieved. VHDL update achieved. Functional test of the 2nd PXI achieved. PXI BOLO SPIRE Electronic & design Achieved. VHDL soft studies. Test software specification writing achieved. Test board configuration study & realisation achieved. Functional test achieved. Stability checked out, prototype demonstration, fabrication launch PXI heater/Supply Design achieved. Manufacturing file ritten. Test software specifications achieved. Test board configuration study & realization achieved. Onboard VHDL software study achieved. PXI part fabrication started week 21 (sub-contractor SPCI & ERTE). PXI Cernox DC & AC Analogue studies & design achieved. Complementary tests achieved. Manufacturing file writing achieved, Test software specifications achieved. Test board configuration study & realisation achieved. Onboard VHDL software study over at 50%. PXI part fabrication started week 21 (sub-contractor SPCI & ERTE). Functional test achieved, Fabrication launch Software Supervision software specification writing. Output & input file configuration specification writing. PXI BOLO SPIRE, PXI HEATER / SUPPLY, PXI CERNOX, PXI TRIGGER IO test software development achieved. Supervision software on going, test with PXI prototypes |
|  | Progress during the month |  |
|  | PXI BOLO: Stability checked out, prototype demonstration, fabrication launch PXI Heaters/supply: stability checked out, prototype demonstration, Fabrication launch PXI CERNOX: prototype demonstration, Fabrication launch SOFTWARE: supervision software development, test with PXI prototypes |

| Part procurement | Status |
| --- | --- |
|  | Declared components list update: edition 13 OP400 qualification review 12/02/02. Fabrication started. Harnesses connector estimation carried out. ATP update with Technologica |
|  | Progress during the month |  |
|  | / |
| Harness | Status |
|  | DCU at JPL test Harness delivered to CEA and sent to JPL Connectors procurement on going Work with the AIV to determine SPIRE test harness in progress |
|  | Progress during the month |  |
|  | SACEE connectors partial delivery DCU harness delivered to CEA and sent to JPL Work with the AIV to determine SPIRE test harness |
| Containers | Status |
|  | Specification available. |
|  | Progress during the month |  |
|  | None |
| AIV | Status |
|  | DRCU development tree available (last version 30/11/2001) DCU Board Test plan writing in progress. DRCU AIV plan in progress. |
|  | Progress during the month |  |
|  | DRCU AIV plan writing, new issue. |
| PA/QA | Status |
|  | DML and DPL draft available. Reference documentation list update on going Requirement Cross verification table achieved |
|  | Progress during the month |  |
|  | Updating of the reference document list. Building of Requirement Cross verification table achievement. Non conformity management |

| Problem Areas | Remedial Actions |
| --- | --- |

| Milestones | Status |
| --- | --- |
| DCU EM QM1 delivery to SAp from JPL | 06/01/2003 | On schedule |
| DRCU QM1 harnesses need date | 09/12/2002 | On schedule |
| LTU DRCU available | 09/12/2002 | Delayed by 2 months |
| SPIRE FPU simulator #1 need date delivery to SAp | 13/01/2003 | On schedule |
| Detector test cryostat delivery to SAp by JPL | 25/11/2002 | On schedule |
| MCU QM1 + simulator need date delivery to SAp | 10/12/2002 | On schedule (TBC) |
| SCU QM1 delivery by SEDI need date | 24/01/2003 | On schedule |
| DRCU QM1 delivery to RAL | 03/03/2003 | Delayed by 1 month: 24/04/2003 |
| SPIRE FPU simulator #2 need date | 28/07/2003 | On schedule |
| SCU QM2 need date | 27/08/2003 | On schedule |
| MCU QM2 delivery to SAp need date | 27/08/2003 | On schedule |
| DRCU QM2 delivery to RAL | 05/01/2004 | On schedule |
| MCU FM delivery to SAp need date | 26/04/2004 | On schedule |
| SCU FM need date | 05/05/2004 | On schedule |
| DRCU FM ready for delivery to RAL | 30/07/2004 | On schedule |

| Documentation progress this month |
| --- |
| Title | Reference | Progress |
| DRCU AIV Plan | SAp-SPIRE-HT-0082-02 | Issue 1.2 |

| Documentation List |
| --- |
| Title | Reference | Version, date |
| Reference documentation |
| SPIRE Instrument Development Plan IIDR | / | Issue 1.1 12/4/2001 IIDR |
| SPIRE Major Milestone List issue 1.3 IIDR | SPIRE-RAL-PRJ-000455 | Issue 1.3 |
| SPIRE Instrument Requirements | SPIRE-RAL-34 | Issue 1.1 10/01/2002 |
| ICD cooler | HSO-SBT-ICD-012 | / |
| SCAL ICD PCAL ICD | HSO-CDF-ICD-011 HSO-CDF-ICD-013 |  |
| Detector SSSD | SPIRE-JPL-PRJ-000956 | Issue 3.1 – draft |
| Shutter SSSD | Not yet | / |
| Instrument Interface Document part A | SCI-PT-IIDA-04624 | 3.0 01/07/2002 |
| Instrument Interface Document part B SPIRE | SCI-PT-IIDB/SPIRE-02124 | 2.2 01/07/2002 |
| SPIRE configurable document tree | SPIRE-RAL-PRJ-00033 | 3.1 03/05/2001 |
| SPIRE product tree | SPIRE-RAL-PRJ-00455 | 1.0 09/11/1999 |
| SPIRE instrument development plan | SPIRE-RAL-PRJ-0035 | 1.0 20/05/2000 |
| SPIRE management plan | SPIRE-RAL-PRJ-00029 | 01/01/2001 |
| SPIRE Data ICD | SPIRE-RAL-DOC-001078 | 1.0 draft1 15/01/2002 |
| SPIRE instrument AIV plan | SPIRE-RAL-PRJ-000410 | 2.1 29/03/2001 |
| SPIRE harness definition | SPIRE-RAL-PRJ-000608 | 1.0 08/07/2002 |
| Management |
| Management plan for the Herschel project. | SAp-FIRST-JLA-0038-01 | 3.0 23/11/2001 |
| Actions list | SAp-FIRST-DR-0050-01 |  |
| DRCU & WIH Development Plan | SAp-SPIRE-JLA-0047-01 | 3.0 27/11/2001 |
| SPIRE product tree | SAp-FIRST-DR-0071-02 | 1.2 |
| WBS Herschel | SAP-FIRST-DR-0043-01 | 2.1 |
| WBS SPIRE | SAP-FIRST-DR-0045-01 | 2.1 |
| SPIRE master schedule | SAp-SPIRE-DR-0053-02 | 3.4 30/09/2002 |
| DCU EM QM1 at JPL detailed schedule | SAP-FIRST-DR-0050-01 | 4.9 30/09/2002 |
| SPIRE FPU simulator detailed schedule | SIG-FIRST-PdA-0052-01 | 13.0 30/09/2002 |
| SCU QM1 detailed schedule | SEI-SPIRE-MM-0049-01 | 11 30/09/2002 |
| LTU & power bench detailed schedule | SAp-FIRST-DR-0069-02 | 3.1 30/09/2002 |
| DRCU |
| DRCU Specifications document | SAp-SPIRE-Cca-0025-00 | Issue 0.92 26/06/2002 |
| DRCU Development Tree | H0030 | 30/11/2001 |
| DRCU ICD | SAp-SPIRE-Cca-0075-02 | 0.7 26/06/2002 |
| DRCU DPU ICD | SAp-SPIRE-Cca-0076-02 | 0.7 26/06/2002 |
| DCU design document | SAp-SPIRE-FP-0063-02 | 0.2 05/07/2002 |
| Test plan DAQ IF | SAp-SPIRE-FP-0067-02 | 0.1 draft |
| Test plan BIAS | SAp-SPIRE-FP-0066-02 | 0.1 draft |
| Test plan LIA P | SAp-SPIRE-FP-0064-02 | 0.1 draft |
| Test plan LIA S | SAp-SPIRE-FP-0065-02 | 0.1 draft |
| SPIRE test configuration, | SAp-SPIRE-LD-0015-01 | 3.0 08/2001 |
| FPU simulator specifications for DCU / SCU test | SIG-SPIRE-PdA-0030-01 | 19/03/2001 |
| SPIRE LTU specifications | SAp-SPIRE-FD-0071-02 | 1.0 22/04/2002 |
| DRCU AIV Plan | SAp-SPIRE-HT-0082-02 | 1.2 23/09/2002 |
| QA |
| Standard product assurance plan | SAp-GERES-Flo-436-00 | 1.0 09/11/2000 |
| SPIRE liste des documents à produire | SAp-SPIRE-Flo-0028-00 | 0.2 15/12/2000 |
| Organisation de la gestion documentaire sur Herschel au SAp | SAp-FIRST-DR-0053-01 | 1.1 06/12/2001 |
| Gestion des documents sur la base Herschel | SAp-FIRST-DR-0072-02 | 1.3 15/04/2002 |
| Procédures de contrôle projet sur Herschel | SAp-FIRST-DR-0125-02 | 1.2 13/05/2002 |
| DRCU FMECA Report |  | Issue 1.0 25/10/2001 |
| Analyse de fiabilité du DRCU | SAp-SPIRE-Flo-0039-01 | 21/08/2001 |
| DRCU processor board PA specification | SAp-SPIRE-Flo-0020-00 | 10/01/2001 |
| Plan d’action de AP du projet Herschel | SAp-FIRST-Abx-0137-02 | Issue 1.1 18/06/2002 |
| Evaluation report for test plan of DCU boards | SAp-SPIRE-JF-0079-02 | Issue 1.0 |