Work Package:	Structure                                                             SPIRE-MSS-REP-001445

| 1. Subsystem Progress Since Project Inception |
| --- |
| Several concepts evaluated for the structure. Base line design decided upon in June 2000. Working on the system implications and implementation since first half of 2001. Continuing to close interfaces with the various subsystems. Started with production drawings in February 2001. The concept of the suspension has been analysed and decided on implementation. Hardware produced and tested, meets specifications. Detailed design continuing and manufacture is continuing. |
| 2. Subsystem Progress This Month |
| Thermal busbar development is continuing. Production drawings are still in progress. Received MKIII units and light baffle from Cardiff. Started the mechanical testing so that the FEA can be completed in early October. MGSE assembly is awaiting HOB simulator – This is due early October. Production of the photometer 2K box spine is still continuing, though the covers have been completed. The redesign of SCAL box is still being debated. Spectrometer 2K Detector box has been completed and is awaiting final inspection. The manufacture of the Optical Bench is continuing. Continuing to have integration team meetings with RAL, to address planning and integration issues. Released Issue 16 of the interface drawing. Redesigned main cone to avoid clash with PACS. |
| 3. Problem Areas | Remedial Action |
| Also other subsystems have problems with them. Thermal busbar suspension has strong non-linear responses Level 1 thermal strap interface with spacecraft still is not confirmed Problems within the SCAL baffle box, forseen by the Optical team (LAM and RAL), have led to some redesign of the SCAL BOX Delivery date now 3 months late – due to additional work on thermal busbar and the scrapping of one set of optical benches. | Development team has been set up to redefine design. Continuing to work to implement design without effecting the schedule. Have produced design for the thermal bus bar itself . Received MKIII units from Cardiff. Stared mechanical charactisation tests before going on to FEA. Production design has started Redesigned the SCAL box . Awaiting confirmation from LAM and RAL at the alignment meeting on 1 October. Constant monitoring of manufacturing progress and preplanning of follow on activities with RAL to minimise impact on whole project. |
| 4. Engineering Activities |
| FEA on thermal busbar and new design of main cone. |
| 5. Design Changes |
| - |
| 6. PA/QA Activities |
| NCR now not necessary as part has been scrapped due to another manufacturing error |
| 7. Subsystem Management Issues |
| - |
| 8. Actions Requiring Immediate Attention |
| - |
| 9. Status of Previous Actions |
| - |
| 10. Activities Yet to be Achieved |
| 11. Milestones | Status |
| February 2002 13-08-2002 01-02-2002 10-06-2003 01-10-2002 6-01-2004 | Interfaces defined and reported STM delivery to RAL CQM FTB enclosure to RAL PFM delivery to RAL PFM FTB enclosure to RAL FS delivery to RAL | Completed now 3 months late-7-11-02 On schedule On schedule On schedule |
| 13. Schedule Changes |
| Due to the thermal busbar design, manufacturing problems, and optical bench checking we are lagging 3 months behind on original schedule. |