Minutes of EGSE Meeting #23

SRON, Groningen, September 24, 2002

Participants:

PACS: Otto Bauer (MPE)

HIFI: Luc Dubbledam (SRON)

SPIRE:	Ken King (RAL)

ESTEC: Bryan Melton, Johannes Riedinger, Kevin Galloway

# Adoption of the agenda

- Minutes and Action Items from last meeting

- EGSE-DPU/ICU testing at IFSI

- AVM-ILT at MPE

- CDMS Simulator, use of ESTEC Simulator

- SCOS 2000/TOPE

- EGSE-CCS (see also Bryan´s E-mail from Sep 9)

- Next meeting/telecon

- AOB

# Minutes and Actions from last meeting

Minutes of last meeting were accepted

Review of Action Items

Status of Action Items at the beginning of the meeting:

| Action | Actionee | Description | Due Date |
| --- | --- | --- | --- |
| EGSE#19-04 | Serge | To provide SPR template | 31 July 02 |
| EGSE#21-02 | HIFI PACS SPIRE | To provide updated/new user manuals for each EGSE component | 19 July 02 |
| EGSE#21-03 | Otto | To provide draft documentation of the baseline EGSE configuration | 15 July 02 |
| EGSE#21-04 | HIFI PACS SPIRE | To provide comments on inconsistencies between the new naming conventions and SCOS | Closed Closed 02 July 02 |
| EGSE#21-07 | Serge | Investigate costs of iLog | Open |
| EGSE#22-01 | Serge | To summarize the flow of actions to be taken to get the next version of SCOS 2000 (2.3e) running |  |
| EGSE#22-02 | Otto | Make sure that the information on patching VIRTUOSO will be distributed to HIFI/SPIRE |  |
| EGSE#22-03 | Luc | To ask Albrecht to assess the amount of work to write a PIPE-Router interface |  |
| EGSE#22-04 | Bryan | To find out reasonable need-date to deliver Instrument-EGSE to integrate with CCS |  |

EGSE#19-04: Closed: Bryan sent E-mail with problem to Serge, they will feed it into ESOC

system.

EGSE#21-02: Closed: SPIRE will send new version of the CDMS Sim end this week with new

manual - Router ICD available including Start Script – SCOS, TOPE, CUS are available as first versions.

EGSE#21-03: Closed.

EGSE#21-04: Closed: Comments were sent.

( AI EGSE#23-01: Bryan to find out final status, due Oct 18, 02

EGSE#21-07: Closed: Still discussion with ESOC, ESOC might supply licenses for iLog.

EGSE#22-01: Closed.

EGSE#22-02: Closed.

EGSE#22-03: Closed: Albrecht estimates that the implementation takes 2 days, the

documentation 2 weeks. CCS test clients will be needed. This is a TERMA task.

( AI EGSE#23-02: Bryan to bring it to the attention of the Project that CCS tests clients are

needed, due Oct 18, 02.

EGSE#22-04: Closed: The need date of the Instrument EGSE is Oct 1, 03. The integration will

take 3 days. The Instrument EGSE always contains the HCSS. We will deliver

two EGSE´s – one for hot standby.

( AI EGSE#23-03: Otto to provide integration plan (2 pages), due Nov 29, 02.

# EGSE – DPU/ICU Testing at IFSI

- PACS: The acceptance test of the DPU took place at IFSI on July 10. The DPU arrived at MPE on Sep9. MPE misses a proper logging of all activities. This might have consequences for handling and testing.

- HIFI: Similar experience. Also at present the science data transmission is not working, but no problem report available from IFSI.

- SPIRE: Problem with science data transmission from Instrument Simulator to DPU. Acceptance test foreseen for Nov 19, delivery to RAL Nov 25.

# AVM – ILT at MPE

- DPU arrived Sep 9, SPU Sep 13 and DEC/MEC including BOLC Sim Sep 16.

- Incoming inspection went well.

- During first tests several problems encountered:

  - 1355 I/F: master-slave problem, PACS AVM´s cannot be turned on in the right sequence. Project contacted for help

  - CDMS Sim: Crashes from time.

  - Router: Router crashes when packets are not picked up by HCSS. Kevin will check what Router does (SPR?).

( AI EGSE#23-04: Otto will distribute on-board S/W loading procedure developed by Erich,

due Sep 27, 02.

5.   CDMS Sim, Use of ESTEC Simulator

- Ken distributed ICD draft 4, new the S/W including user manual will be delivered to PACS and HIFI on Sep 27.

( AI EGSE#23-05: Ken will send CDMS Sim ICD, draft 4 to Bryan, due Sep 27, 02.

- The test bed at ESTEC should be used to Test the DPU/ICU 1553 I/F. In principle it could also be used to test the CDMS Sim.

- IFSI would like to have the test bed at IFSI and run the tests there. Brian informed us that the test bed is based on a desktop PC b, but had no further information.

- Instrument teams have to sign test plans – Sergio split the 1553 test plan into a H/W part and put the rest into the OBS test plans of the three units.

( AI EGSE#23-06: Sergio to update all test plans ( 1553 H/W and three OBS) and send then to

the instrument teams, due Oct 04, 02.

( AI EGSE#23-07: Brian to check if description of ESTEC test bed is available, due Oct 04, 02.

# SCOS-2000/TOPE

- SCOS 2000 v2.3e has been installed at RAL under Linux (Zuse). Serge wrote protocol about installation. It was send to Luc.

( AI EGSE#23-08: Bryan to distribute installation protocol, due Sep 27, 02.

- LOGICA patch (TC History, OOL) is not included in the present delivery. It should be sent out by ESOC on Sep 24. LOGICA patch will never be a part of the official SCOS system. They will migrate to CORBA interfaces and we have to follow.

- P. Estaria raised the question if we get enough SCOS 2000 support from Bryan´s  team (Serge). It was the general feeling that the support is good and fast if Serge is there, but he is very often on mission and no deputy is available.

# EGSE – CCS

- Bryan explained his E-mail from Sep 9, which foresees a direct connection between EGSE and CCS for the transmission of command sequences.

- The instrument teams and HCSS (Johannes, Kevin) agreed to the concept. Bryan confirmed that his proposal has the blessing of O. Piersanti.

( AI EGSE#23-09: Erich, John and Albrecht will come up with a feasibility analysis of Bryan´s

proposal, for further information Bryan can be contacted, due Oct 30, 02.

# Next Meeting/Telecon

EGSE#24 (Telecon): Tuesday, November 12, 14:00 (CET)

# AOB

- PACS would like to have a Data Rate Monitor. It could be part of the CDMS Sim or the Router.

( AI EGSE#23-10: PACS to write URD and distribute it, due Oct 30.

ANNEX

Status of Action Items at end of meeting

| Action | Actionee | Description | Due Date |
| --- | --- | --- | --- |
| EGSE#23-01 | Bryan | Find out final status of naming conventions (Alcatel – SCOS 2000) | 18 Oct 02 |
| EGSE#23-02 | Bryan | Bring it to the attention of Project that test CCS clients are needed for the implementation of the PIPE protocol on EGSE side | 18 Oct 02 |
| EGSE#23-03 | Otto | Provide EGSE-CCS integration plan | 29 Nov 02 |
| EGSE#23-04 | Otto | Distribute on-board S/W loading procedure developed by Erich | 27 Sep 02 |
| EGSE#23-05 | Ken | Send CDMS Sim ICD, Draft 4, to Bryan | 27 Sep 02 |
| EGSE#23-06 | Sergio | Update all 1553test plans (H/W, 3 OBS) and distribute them | 18 Oct 02 !! |
| EGSE#23-07 | Bryan | Check if description of ESTEC 1553 test bed is available | 04 Oct 02 |
| EGSE#23-08 | Bryan | Distribute SCOS 2000 installation protocol from Serge | 27 Sep 02 |
| EGSE#23-09 | HIFI PACS SPIRE | Produce feasibility analysis of Bryan´s proposal for a transmission of command sequences from EGSE to CCS | 30 Oct 02 |
| EGSE#23-10 | PACS | Write Data Monitor URD and distribute it | 30 Oct 02 |