SPIRE-RAL-MOM-001570

SPIRE Project Team Meeting, RAL, 17 March 2003

Present:   Matt, Eric, Doug, Dave, Eric, Anso, John

STM-CQM status:

- MSSL doing fit checks at the moment.  A few misfits that need work-arounds.  Delivery in about a week.

- Vibration fixture has been designed by MSSL, quotes available, still needs to be out for manufacture.

- MSSL schedule delays overall - historically due mid-2002 - now April 2003

- Need for continuing involvement from Berend

- Matt and Eric need to visit MSSL to discuss schedule, programme, resources with Berend and Alan on 28 or 31st.

- Black tiles: 
-  MSSL need to specify shape and size of tiles
-  New process needs to be qualified - cold vibration problem
-  MSSL have to design the tiles - check with Berend
-  Bonding to alochrome surface needs to be established
-  Someone needs to be in charge of planning this - agreed it should be Eric to define the plan and ensure it gets done

Telecon with Berend:

STM schedule:

- RAL may get structure next week

- Early vibration test depends on fixture delivery - test schedule for April 23 - looks a bit tight

- Berend:  Problem with mass saving needed for the fixture - had to do that.  Two quotes in - Electromech (usually late) and another (6-8 weeks).  Third quote today - order will go out today.

- Eric:  If not going to get fixture in 4 weeks, must start something else on that timescale.  Eric will look into that.

- Cheap-and-cheerful slip table fixture? OK but direction reqd for detectors won't be accommodated - but can discuss with Dave Rippington later this week - maybe split the test.

- Black tiles:  as discussed . . .

- Level-0 interface tests:  IDH tests to be done start April.  John working hard on Gaia . . .

- Doug:  will do test in AIV dewar for cooldown - will take a couple of weeks

- Matt:  is level-0 plan and schedule all under control -

- Physical design of isolating joint between cold straps and optical bench - John working on this.

- Matt:  when does this need to be done for STM-CQM?

- Eric:  needs to be designed and built by July

- Electrical isolation of 2-K box:  Fix for CQM is kapton sheet - will be used for PFM if OK.

- Action:  Eric to follow all up

- MSSL support of mechanical integration needs to be confirmed.

- Level of effort at RAL:
- Pete needed for STM/CQM thermal testing  - CBB, SCAL integration
- Canadians
- RAL and MSSL technicians
- JPL needed for BDA integration

- Check if Pete sent list

- Status of other STM/CQM deliveries:

- SMEC:  Supposed to be available when needed - to be checked at next telecon

- Mirrors:  here

- Cooler:  Here

- SCAL:    should be available

- Filters:    OK - not needed

- Harnesses:  Delays in getting model from MSSL and Tekdata making the horse

- BDAs:  To be despatched this week from JPL.

- Conclusions:  BDAs  (CQM) and harnesses may be the pacing items.

Thermal design:

- Anso:  Astrium still having problems with RAL model

- Astrium now have full RAL model - they'll try that and get back on Wednesday

- Their new model has HOB 2.5-K lower

- ESA wants full 48-hr cycle to be run

- Astrium policy is now to stop work on SPIRE model and switch over to HIFI model

- Action:  John to draft note to Collaudin et al. to emphasise importance of sorting out 
this issue - to be sent by Matt and Eric.  Judy to fax.

- Options for recovery:
-	Anso did best case analysis and achieved 48 hrs with 1.7 evaporator temperature
-	48 hrs barely doable
-	Anso to look at how it would improve if HOB temp comes down by 2.5 K
- 	Need to update cooler model with Lionel's latest results

- Conclusion

- Action: Anso to do analysis with - 2.5 K  - this week

- Anso to update cooler model: requires Lionel's new data - probably one working week after she gets the new data - say 2 weeks from today

- Action on Anso to estimate how long it would take to update the model

- Astrium have to sort out the thermal modelling

- We have to continue Level-zero conductance minimisation

- Option of having separate strap for pump  . . . . three strap option . . .  Action: Doug will speak to Lionel about slow pump cool-down option

- We'll review it again in two weeks time

- Overshielding inside the CVV has always been there - not just since the grounding review.

- It was in IID-B 2.0 31 July 2001

- Wasn't in the ITT that ESA sent to industry.

- Grounding review just allowed us to put details on implementation.

- Thermal impact was said to be the problem 1 year ago - turns out to have been small, now it's schedule

- Is the overshield needed since we have shields already:

- Response:  our shields = analogue ground plane, exposed at both ends.  Nano-V signals over large distances would lead one to triple rather than single shields.

- Impossible to model bolometer susceptibility - have to do it by experience

- Annex to ESA fax is misleading about system susceptibility

- Our design is based on best common practice

- We will test with what we have, so CQM is first test at system level on anything representative

- If CQM reveals a problem . . . . our CQM tests nullified; and recovery needed - the first test useful test of SPIRE at system level would be in the PFM.

- Mention their presence at the grounding review - raised thermal objections, not schedule objections

- We will not adopt any changes to our designed hardware

- Without the shield we of course need to substitute low-impedance wires from CVV connectors to the FPU - need for industry to liase with us on this

- EMC working group meeting on 26th

Next meeting:

Summary of actions

| Action | Responsible | Date | Status |
| --- | --- | --- | --- |
| Define plan for development of black coating, monitor and progress | Eric | First tiles required for the STM in mid July | Open |
| Consider schedule work arounds if vibration fixture is not available in time | Eric | 24/3/03 | open |
| Follow up Electrical isolation of 2-K box and L0, L1 straps | Eric | 31/3/03 | Open |
| Draft note to Collaudin et al. to emphasise importance of sorting the thermal design - to be sent by Matt and Eric. Judy to fax | John | 24/3/03 | Closed, Fax sent |
| Look at how hold time would improve if HOB temp comes down by 2.5 K | AnneSo | 24/3/03 | Open |
| Update cooler model with Lionel's latest results | AnneSo | 31/3/03 | Open |
| Estimate how long it would take to update the thermal model | AnneSo | 24/3/03 | Open |
| Speak to Lionel about slow pump cool-down option | Doug | 24/3/03 | Open |