Current IHDR documentation status and relevant actions

May 27

Green = Document available	Blue = updates 		Red = highest priorities

| No. and Priority | Document | Responsible | Current Status | Plan |
| --- | --- | --- | --- | --- |
| Top-level requirements documents |
| 1 3 | Scientific Requirements Document | Matt | No update needed |  |
| 2 2 | Instrument Requirements Document | Bruce | Routine update via ECR needed: - Removal of shutter - SMEC spec. mods - BSM latch removal - Other small ones | ECRs to be collated and new doc to be ready by May 23. Not done yet. To be done for Friday 30. |
| 3 2 | Calibration Requirements Document | Bruce | - Ground calib sections OK - In-flight sections need some attention - will not be done until after IHDR. Will workn closely with Sarah Leeks over the next year. | No update for IHDR. |

| Instrument Design Description and Development Plan |
| --- |
| 4 3 | SPIRE Design Description Document | Doug (+ Matt) | Needs to be updated | Still to be done by end May. Matt to update sensitivity section. Matt to update sensitivity Freeze Doug's version in pdf by Friday. |
| 5 1 | Instrument Development Plan | Ken/Eric | To be updated. Will be in the same format as for the IBDR. | Eric needs to update urgently. Five parts: 1. Instrument Development Plan - No change; bu noite to be provided outlining propsed changes - include system level and key changes to subsystemn deliveries (Eric). Aim to have this by Friday. 2. Milestone list - Needs updating - do so wrt new plan. Not many things are different. Try for Friday. 3. Schedule - Could go as is. CEA deliveries need to be included. Aim for Friday. 4. Subsystem Dev. Plans: - Check what's available. - See how out of date it is. - Default is to use current ones. - Eric to send e-mail to subsystems asking for high priority docs. 5. Subsystem schedules - Subsystems to eb asked to update. |
| 6 3 | EMC control plan | Doug | Update needed to include grounding scheme change and modelling/test plans | Doug to produce addendum to existing document explaining changes and work in progress by May 15. No progress. Doug and Bruce to write this by May 23. Nothing available - review status Friday 30th. |
| 7 3 | Microphonics control plan | Doug | Working version to be produced for review | Change plan: produce test specification for CQM. Outline to be produced by Doug ready by May 30. Still on schedule. |

| IID-B and related documents |
| --- |
| 8 3 | IID-B | John D. | Under Alcatel control - we’ll provide status report and list of important items/issues from our point of view. | OK. John working with Industry on next version. |
| 9 1 | Thermal Model document | AnSo | Version is now out for review by Proj. Team. Will be circulated for checking by 11 April. | Doc. will be left as is and ECR raised for changes. |
| 10 1 | FPU Mechanical Model | Berend | Status to be checked with Berend on his return (24th) | Include new subsystem spec note in IHDR pack. Action on Berend to write short top-level account of the model by June 1. No update. Berend working on getting subsystem levels. Eric to ask Berend to as a minimum: subsystem levels as a note; test report; pref desc of model also - needed by 3 June. |
| 11 1 | Harness Definition Document | Doug | Issue 1.1 now out. 1.2 will be produced for the review. Minor updates. | ECRs will be produced routinely. New version to be ready by May 30. V1.1 is out for signature. If 1.2 available then OK. OK. |
| 12 3 | Stray light model document | Tony R. | No update needed. Internal SPIRE description is still correct but not the external parts - make clear to RB. | Technote by Marc Ferlet verifying Astrium ASAP model to be included in doc list. |
| 13 1 | Budgets spreadsheets | John | To be updated - routinely. | Freeze May 30. |
| OBS |
| 14 1 | OBS URD | Sergio | Issue 1.1 requires an update - IFSI have an action to do that. | Bruce and Ken to liase with Sergio. To be finalised by Apr. 28. RAL have commented on latest version. Action: Ken to check progress with Sergio. Old version is adequate if needed. Action: Ken to give Sergio deadline of May 15 to produce new version. New version now available - to be issued by May 30. To be issued as is. Ken will focus on Dev. Plan with Eric. |
| 15 1 | OBS Architectural Design | Riccardo | Exists in draft. Needs a lot of work. | Now agreed that final version will be available mid-June - to be sent in late. Ken has advised Sergio on contents . Review status at telcon on June 3. |
| 16 3 | Operating Modes Document | Bruce, Matt, Sunil | Minor updates needed. Parallel mode needs to be sorted out. Telemetry rates need to be reviewed and updated using Ken's input. | No update planned. Some bits need updating as part of normal work |
| 17 1 | Operating the Instrument Document | Sunil | In draft form and needs updating. More detail on low-level ops. Based on latest command list. | Sunil is working on it To be reviewed on May 23. To be available on Friday May 30. Freeze by June 3. |
| 18 2 | SPIRE Data ICD | Ken | Was issued for DPU acceptance tests. But needs further update based on CEA ICD. | Normal work. Latest version will be provided for the review. |
| AIV Plan |
| 19 1 | Warm Electronics integration plan | Eric | Needs updating. Dave and Samuel are working in the detailed functional test plan next level of detail) | Bruce has sent new model philosophy plan to Saclay for comment - to be reviewed at next telecon. Then plan needs to be documented for IHDR. Eric trying to arrange telecon - report on Friday May 30 |
| 20 1 3 | FPU integration plan | Chris Eric | FPU will have been integrated. MSSL responsibility. Subsystem integration procedures need to be added (maybe just put in a list) | Review status on April 28. Chris is updating plan based on STM. New version May 30. Chris's version expected Friday - to be frozen as received. |
| 21 1 | Alignment Plan and Alignment Procedures | Kjetil | Will have been carried out. No update needed. Will be refined as procedures done. | Dave has produced working version and Marc has commented. Frozen. |

| 22 1 | Instrument-Level Test Plan | Dave Smith Bruce | STM: to be reviewed. | Dave has produced draft ECR 55. Eric to check with Dave and report Friday May 30. |
| --- | --- | --- | --- | --- |
| 23 1 | Manufacturing Flow Charts | Eric Clark | Already contained in ILT plan - no need to produce a separate document. |  |
| GSE |
| 24 3 | GSE Overview | Ken/Bruce | No update needed on IBDR version |  |

| PA |
| --- |
| 25 2 | SPIRE PA Plan | Eric Clark | Has never been approved by ESA. ESA (PO) comments to be taken into account. | New version to be available by May 15. Done. |
| 26 2 | SW PA Plan |  | Included in PA plan |  |
| 27 1 | FMECA | Bruce | Update needed. Harnesses to be included. Doug has done harness/detector analysis. Bruce will review and interpret this. Ken and Bruce doing system aspects. | Provide Doug's pixel mapping note. Subsystems: fully redundant except for cooler. Bruce to update watever was submitted for IBDR. Include System Interface FMECA that Bruce did in Nov. Review status on Friday May 30. |
| 28 1 | Configuration Management Plan |  | No update needed. Same as IBDR. | OK |
| 29 2 | Cleanliness Control Plan | Bruce | Comments from Jan. to be taken into account. | Procedures have been written and they will be referenced. Today's version can be submitted. |
| 30 1 | Configured Items Data List | Eric Clark | Exists for the STM/CQM and is under config control (not "frozen"). Not in ESA's preferred format but does contain needed information. Will not be reformatted. | Will be reviewed and updated for IHDR by May 30. Fereeze whatever Eric produces on May 30 |
| 31 1 | Critical Items List | Matt and Eric Sawyer | To be updated using format ESA have suggested. | Matt to produce a version for May 30 |
| 32 2 | Safety submission/ analysis | Eric Clark | Submission has been produced and submitted. Lionel is to send cooler input this week. | Lionel's note looks OK - Eric will include it in the SPIRE submission and send to industry. Freeze on May 30. |
| 33 1 | Worst Case Analysis |  | DRCU: Limited version in DRCU review documentation. DPU: Ken and Eric C to review new version that has been received. | Eric made some comments to IFSI. No response yet. Eric will contact Eric C to provide the docs to Eric S by May 15. In hand (Eric C). To be sorted out by 23rd if possible. No update - aim to freeze on May 30. |
| 34 2 | Part Stress Analysis and derating analysis |  | Contained in Warm Electronics PA plans. Also needed for SPIRE-provided harnesses. | Doug to write note covering internal FPU harnesses May 23rd. Check status on Friday 30th. |
| 35 1 | FDIR | Bruce | To be written before H/W-S/W interaction analysis. Bruce and Ken have started. | Fault tree analysis has been started. High priority for Bruce and Ken. Ken and Bruce working on it - but a lot to do. Document to be issued as technote describing state of work in progress. Needs to be available b y June 8th. |
| 36 1 | HW/SW interaction analysis | Ken and Bruce | To be written based on format agreed with Jan. Significant work needed | Same exercise as FDIR. |
| 37a-e 2 | a EEE Parts list, b PAD sheets c DML d DPL e DMPL | Eric Clark | PAD sheets: IFSI, CEA to be contacted for latest information | To be done for May 23. Freeze on May 30th. |
| 38 1 | Verification Control Document | Eric S./Bruce | "Verification Plan" was issued for IBDR. AIV plan includes basic verification matrix. | Covered eleswhere - is being covered in the AIV plan and the ECR on it. |
| 39 3 | Test Procedures |  |  | Dave to provide the available test procedures on May 15. Still to be done. Revised deadline - May 30. |
| 40 1 | NCR and RFW status lists | Eric Clark | Snapshot to be provided. As many as possible will be closed out. | Eric C. to send Eric S. the current list on May 15. In hand - freeze May 30 |
| For each subsystem |
| 41 2 | All DDR Document sets with any updates made since the DDR | Eric | Each subsystem to provide updated versions (if appropriate) of their DDR document sets. Eric Sawyer will contact subsystem managers on this. | DRCU - OK. BSM - What we have today is OK. Proposal: Ask each SS Manager to provide a full set. Deadline May 23rd. Matt to e-mail tomorrow. Eric to send email asking for update. |
| 42 1 | All DDR Review Board Reports (several need to be formally issued) | Eric/Bruce/ Doug | BSM: Done (Doug) DRCU: done (Matt) Cooler: done (Bruce) Calibrators/Filters - to be done (Bruce) - revise to 23rd. Structure (Eric) - to be done - by 23rd. DPU - done (Ken) 300-mK - done (Doug) JPL: Include NASA review reports SMEC/Mirrors - to be done (Bruce) - done. | Structure to be done by Eric - June 5. Others to be frozen on Friday May 30. |
| 43 3 | List of available STM EIDPs and Acceptance Review Minutes as available. | Eric Clark |  | Have cooler, BSM, Mirrors, Structure, SMEC, JPL (some material). Cardiff to be provided: Freeze on Friday. |
| 44 1 | Technical reports to demonstrate subsystem design compliance and maturity. | Bruce/Eric S. | Eric S. to contact subsystems requesting them to provide all relevant reports. PT to review and select relevant docs for review package. | Bruce to send e-mail to all subsystems specifying minimum set. Freeze on Friday. |