SPIRE-PAC-MOM-001663

Minutes of EGSE Telecon #29

April 24, 2003

Participants:

PACS: Otto Bauer (MPE)

HIFI: Luc Dubbledam (SRON)

SPIRE:	Ken King, Sunil Sidher (RAL)

ESTEC: Bryan Melton,  Kevin Galloway

Alcatel: Felix Chatte

# Adoption of the agenda

- Minutes and Action Items from last meeting

- TOPE implementation status

- PIPE implementation

- Work packages and schedule

- IEGSE/CCS integration

- Next meeting/telecon

- AOB:

  - SCOS version philosophy

  - MIB: Event Packet structure

  - OBSM questionnaire

  - CDMS: 1553 problem

  - DMWG: MoM still missing

# Minutes and Actions from last meeting

Review of Action Items

Status of Action Items at the beginning of the meeting:

| Action | Actionee | Description | Due Date |
| --- | --- | --- | --- |
| EGSE#23-03 | Otto | Provide EGSE-CCS integration plan | April 30th 2003 |
| EGSE#26-03 | Otto | Update note on CCS interface | April 11th 2003 |
| EGSE#27-03 | Otto | When IFSI have provided a DPU/UCU Spacecraft Interface Acceptance Test Plan, Otto will organise a telecon (Instruments + Stefan Theurey) | TBD Theurey had no time to read document |
| EGSE#27-06 | Felix | To provide generic data | 31st May 2003 |
| EGSE#28-01 | Serge | To circulate the Siemens’ report on feasibility of implementing Option 4 from the TOPE meeting | 4th April 2003 |
| EGSE#28-02 | All instruments | To confirm that the modifications to the instrument TOPE (Option 4) are acceptable | 4th April 2003 |
| EGSE#28-03 | Bryan | To confirm project acceptance of TOPE modifications (Option 4) | 11th April 2003 |
| EGSE#28-04 | Felix | To check whether it is confirmed that it would be possible to use CCS/light to test the implementation of the PIPE protocol | TBD |
| EGSE#28-05 | Felix | To contact Mr Dubois to see how OBSM is implemented in CCS/light | TBD |
| EGSE#28-06 | Bryan | To clarify if ESOC can deliver 14 ILOG licences (PACS:5 SPIRE:5 HIFI:4) | TBD |
| EGSE#28-07 | Felix | To copy the fax regarding Naming Convention to Johannes | TBD |

EGSE#23-03: Not yet due.

EGSE#26-03: Closed: See e-mail OHB, 22 Apr 03: EGSE/HCSS to CCS “uplink” interface

EGSE#27-03: Still open: No reaction from Project yet.

EGSE#27-06: Closed: Fax, H-P-ASP-LT-3014, 18 Apr 03

Felix asked the Instrument Teams to comment if they have new ideas.

MIB´s from all instruments are available. Additional identifiers are contained in the MIB ICD file.

( AI EGSE#29-01: Erich to send PIC.dat file to Felix, due 24 Apr 03.

( AI EGSE#29-02: Kevin to send instrument MIB´s to Felix, due 25 Apr 03.

EGSE#28-01: Open

EGSE#28-02: Closed: All Instrument Teams agree to TOPE Option 4

EGSE#28-03: Closed: Bryan confirmed that Project accepts to implement Option 4

EGSE#28-04: Open: See Chapter 6

EGSE#28-05: Closed: See e-mail Felix, 17 Apr 03, OBSM Management

EGSE#28-06: Open: But Bryan believes that ESOC will take care of it

EGSE#28-07: Closed

3.   TOPE implementation status

Bryan reports that:

- Serge is at present visiting Siemens Vienna for the TOPE Option 4 implementation kick-off.

- Implementation will be completed end June.

- First draft of user documentation will be distributed end May.

- Installation on our systems could take place in July

# 4.  PIPE implementation

- SoW from Luc and comments from Albrecht are available.

- Luc pointed out that Albrecht needs a CCS (simulator) with PIPE implementation. Only then he will start implementing.

- TERMA will have the acceptance of the PIPE protocol in June.

( AI EGSE#29-03: Luc to check if Albrecht can do the implementation in July, due 15 May 03.

( AI EGSE#29-04: Bryan and Felix to comment SoW, due 15 May 03.

5.   Work packages and schedule

- We should try to finish everything in July.

- IEGSE/CCS integration

- According to schedule CCS light should be delivered to Astrium end July.

( AI EGSE#29-05: Felix to confirm date and make sure that time will be set aside for IEGSE

integration, due 31 May 03.

( AI EGSE#29-06: ICC´s to agree on IEGSE H/W configuration and who will provide first set,

Telecon: 23 May 03, 10:00 CEST.

# 7.   Next Meeting/Telecon

EGSE#30 (Telecon): Tuesday, 3 June 2003, 15:00 CEST

# 8.   AOB

- SCOS version philosophy:

  - Astrium will use SCOS v2.3 for the CCS.

  - The ICC´s might upgrade to higher versions independently. This might lead to problems when working later with ESOC.

  - Felix would be in favour of common upgrades. Ken Ken points out that we could upgrade independently as long as the ICD´s (SCOS, MIB) don´t change.

  - Felix says that MIB ICD v5.1 is the baseline. In addition the display definitions are also stored in the MIB.

( AI EGSE#29-07: Felix to raise SCOS problem to Project level, due 31 May 03.

  - Sunil mentioned that the MIB discrepancies are summarized in the Tailoring Notes.

( AI EGSE#29-08: Bryan/Serge to find out status of these Tailoring Notes, due 15 May 03.

  - Sunil mentioned that in case of the LOGICA patch (TC History, OOL) the system has to be rebuilt for each new release.

( AI EGSE#29-09: Bryan to find out if and when LOGICA patch will be permanent,

due 15 May 03.

- MIB: Event Packet structure:

  - Is converted in PIC.dat file, see also MIB ICD. Event packet has two ID´s. Conflicts should be resolved by Project.

- OBSM questionnaire:

  - Felix said that there will be a workshop beginning of May. TERMA will come up with a questionnaire concerning the configuration of the different on-board hardware platforms.

( AI EGSE#29-10: Felix to provide questionnaire to ICC´s, due 31 May 03.

- CDMS simulator:

  - After DPU start-up the CDMS bus controller has to be reset manually. Ken said that this a general DPU/ICU problem and SPIRE raised a SPR. IFSI has to lokk into this problem.

- DMWG: MoM still missing

  - Nobody received the MOM. Patrice was contacted.

Status of Action Items at end of meeting

| Action | Actionee | Description | Due Date |
| --- | --- | --- | --- |
| EGSE#23-03 | Otto | Provide EGSE-CCS integration plan | 30 April 2003 |
| EGSE#27-03 | Otto | When IFSI have provided a DPU/UCU Spacecraft Interface Acceptance Test Plan, Otto will organise a telecon (Instruments + Stefan Theurey) | TBD Theurey had no time to read document |
| EGSE#28-01 | Serge | To circulate the Siemens’ report on feasibility of implementing Option 4 from the TOPE meeting | 30 April 2003 |
| EGSE#28-04 | Felix | To check whether it is confirmed that it would be possible to use CCS/light to test the implementation of the PIPE protocol | 31 May 2003 |
| EGSE#28-06 | Bryan | To clarify if ESOC can deliver 14 ILOG licences (PACS:5 SPIRE:5 HIFI:4) | 31 May 2003 |
| EGSE#29-01 | Erich | Send PIC.dat file to Felix | 24 April 2003 |
| EGSE#29-02 | Kevin | Send instrument MIB´s to Felix | 25 April 2003 |
| EGSE#29-03 | Luc | Check if Albrecht can do PIPE implementation in July | 15 May 2003 |
| EGSE#29-04 | Bryan, Felix | Comment on PIPE SoW from Luc | 15 May 2003 |
| EGSE#29-05 | Felix | Confirm date of CCS/light availability and make sure that time will be set aside for IEGSE integration | 31 May 2003 |
| EGSE#29-06 | ICC´s | Agree on IEGSE H/W configuration and who will provide first set | Telecon, 23 May 03, 10:00 CEST |
| EGSE#29-07 | Felix | Raise SCOS version problem to Project level | 31 May 2003 |
| EGSE#29-08 | Bryan,Serge | Find out status of MIB Tailoring Notes | 31 May 2003 |
| EGSE#29-09 | Bryan | Find out if and when LOGICA patch will be permanent | 15 May 2003 |
| EGSE#29-10 | Felix | Provide OBSM questionnaire to ICC´s | 31 May 2003 |