## Slide 1
Critical Items List Matt Griffin Cardiff University

## Slide 2: Critical Items List
• Based on SPIRE-UCF-PRJ-001138, Issue 2.0
• List of issues requiring action to maintain the project schedule and the instrument development plan and scientific capabilities
• They receive attention from the Project Team in consultation with the relevant subsystem groups, ESA, and industry
• Progress is tracked in regular Project Team meetings, ad hoc meetings and telecons as appropriate
• Each item is the responsibility of one particular individual in the Project Team
• Each area has a plan for resolution within a specific period or for continuing management
• More details on most to be presented at this meeting

## Slide 3
1. SPIRE Instrument Schedule
• Original development plan must be adapted if PFM is to be delivered on time
• On-time delivery of the original CQM is not feasible without untenably limited and risky programme
• An alternative plan has been devised and proposed to ESA and Industry in April, and described in detail for this review
• It is already being implemented (SM/AM programme)
• Purpose of this adapted plan: to protect as much as possible the on-time delivery of the PFM • Revised programme has pros and cons
• Problems with subsystem deliveries will need to be solved in any scenario

## Slide 4
2. SM/AM/CQM Programme
• First assembly and test of many subsystem and system elements
• Many “small” problems to be sorted out • Project Team places high priority on addressing these issues sometimes at the expense of other work
• The schedule is vulnerable to any problems with AIV facility

## Slide 5
3. DRCU Development Plan
• Original DRCU development plan involves waiting until QM design verified by instrument CQM tests before starting PFM programme.
• This is now incompatible with the SPIRE Instrument schedule and with on-time PFM delivery
• Discussion and analysis of various scenarios has been taking place since DRCU review in March
• This issue exemplifies the general issue of risk-cost-schedule tradeoffs in SPIRE (and Herschel-Planck) • To be highlighted at this review
• SPIRE asks the Review Board to formulate an unambiguous recommendation on this issue

## Slide 6
4. FDIR
• Slow progress due to lack of resources and late information from subsystems
• All information is now available, and additional effort is being deployed
• HW-SW Interaction Analysis now available

## Slide 7
5. Spacecraft Thermal Interfaces
• Thermal performance is critical for SPIRE’s scientific performance
• Problems with cooler hold time, temperature stability and absolute detector temperature
• Continuing iteration between SPIRE/Industry/ESA on SPIRE requirements and interfaces • Pragmatic approach being adopted with industry/ESA
• SPIRE is implementing all possible measures to improve thermal performance - see also 7 (FPU support redesign) and 8 (SPIRE Level-0 strap interface)

## Slide 8
6. EMC: Harness overshielding
• SPIRE grounding scheme requires overshielding on cryoharness inside CVV
• This requirement is not formally accepted by the ESA Project
• In April SPIRE requested reconsideration of this decision based on high risk to scientific performance • Practical discussions with industry may result in workable solution

## Slide 9
7. FPU and Level-0 Detector Box Supports
• Thermal isolation of the FPU and detector enclosures needs to be improved for better thermal performance • A programme has been started to develop carbon fibre supports to replace current stainless steel supports • Major late design change • New supports will not be ready for the CQM – qualification will have to be on the PFM

## Slide 10
8. SPIRE Level-0 Strap Interface
• Current interface design is inadequate and must be changed and proven in time for CQM cold vibration test
• Pressure of work on structure and recovery from major contractor bankruptcy has delayed redesign • Improved design now being developed with objective of installation in CQM

## Slide 11
9. FTS Mechanism Vibration Qualification
• SMECm design was not compatible with vibration levels predicted by FEA model (by a factor of four)
• Reduced vibration levels after SM instrument vibration tests
• Current design should now be compatible
• Qualification tests will take place at unit level before delivery of the PFM SMECm

## Slide 12
10. BDA Qualification
• BDA qualification and test programme have been severely delayed due to problems with Kevlar supports for 300-mK stage - now have major strain wrt future delivery dates.
• Successful cold vibration has now taken place (but some Kevlar fraying)

## Slide 13
11. JFET Noise and Power Dissipation
• For best noise performance (~ 7 nV Hz-1/2), JFETs need to be operated at about 120 K. • Dissipation needed in photometer mode (worst case) ~ 70 mW (allocation 42 mW).
• CQM tests will clarify severity of the problem
• Power can be reduced at the expense of higher noise, or some FETs can be switched off
• Perforated membranes could eliminate problem – but not baseline for cost/schedule reasons
• Thermal isolation of JFET rack being studied at RAL

## Slide 14
12. 300-mK Thermal Strap Supports
• 300-mK thermal strap system light-baffle and thermal strap support unit failed due to Kevlar friction under warm vibration of the instrument SM
• MRB established cause as a workmanship problem but approved design improvement
• New design now in manufacture and will be tested at unit-level before installation in CQM in mid-August

## Slide 15
13. FPU Internal Black Coating
• Qualification of suitable black compound is not yet complete • Design and manufacture of the black tiles to be installed in the FPU has yet to be carried out
• This programme has been slowed down by 300-mK thermal strap recovery programme • A work-around will need to be formulated to qualify for use on PFM

## Slide 16
14. Correction of Mirrors
• CQM CM3 mirror is misaligned by 0.5o and two others have small misalignments
• LAM are having CM3 remade – foreseen to be available for retro-fit in the CQM • In the worst case, CQM programme will use existing mirrors with compromised testing capabilities

## Slide 17
15. Filter Availability
• Production problems with large area filters have now been solved
• AIV and CQM instrument filters now in production – schedule is critical after delays due to production difficulties; top priority for filter production team
• Schedule for on-time delivery of PFM filter set is very tight and will be closely tracked by the Project Team

## Slide 18
16. Microvibrations
• No update since IBDR
• Bolometers and SMEC position sensor potentially vulnerable to microvibration noise
• Analysis  levels of vibration due to the spacecraft should not pose a significant problem, but uncertainties are large
• Step-and-integrate FTS modes (less sensitive to microphonics) can be implemented
• Limited tests will be done on CQM and PFM

## Slide 19
Reminder: IBDR Critical Items List
Spacecraft interfaces
BDAs - Development Plan and Schedule - BDA vibration levels
300-mK thermal straps
FPU Structure schedule
Microvibrations
DRCU Development Plan and Schedule
DRCU mass
EMC
BSM Development Plan
UK Project Team Costs
OBS effort at IFSI
Shutter programme
AIV Facility
FMECA/FDIR