Work Package	PCAL                                                                  SPIRE-UCF-REP-001781

| 1. Subsystem Progress Since Project Inception |
| --- |
| Haller-Beeman source identified which meets SPIRE requirements PCAL design complete |
| 2. Subsystem Progress This Month |
| PCAL design complete. Enclosure drawings in manufacture (STM & CQM). DM, STM & CQM sources in manufacture (DM will be used for lifetests). DM source received. |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| STM & CQM enclosures in manufacture. DM, STM & CQM sources in manufacture. |
| 6. Design Changes |
| Design completed. |
| 7. PA/QA Activities |
| PA database now in use. DML & DPL in preparation. |
| 8. Actions Requiring Immediate Attention |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones | Status |
| 5/12/00 | QMW source review | Complete |
| 21/09/01 | Prototype source testing complete | Complete |
| 19/09/01 | Final interface definition from ATC | Complete |
| 22/05/01 | Calibrators design review (internal) | Complete |
| 10/6/02 | STM (DM) PCAL delivery to ATC | Estimated del. 6/12/02 – delivery direct to RAL |
| 30/01/02 | CQM PCAL design review (internal) | Complete |
| 3/9/02 | CQM PCAL to ATC | Estimated del. 20/12/02 – To be agreed with ATC |
| 18/10/02 | PFM calibrators design review | Rescheduled for late January 2003 |
| 26/5/03* | PFM PCAL to ATC | Estimated del. 21/5/03 |
| 7/1/04* | FS PCAL to ATC | Estimated del. 12/9/03 |
| 13. Schedule Changes |

Work Package	SCAL

| 1. Subsystem Progress Since Project Inception |
| --- |
| CQM design complete – passed DDR All STM and CQM components complete. |
| 2. Subsystem Progress This Month |
| DM/STM model assembled and tested thermally. Agrees well with thermal model. Thermal model being modified to model & optimise warm-up sequence, rather than just constant applied power. |
| 3. Problem Areas | Remedial Action |
| None |  |
| 4. Subsystem Management Issues |
| CPP parts will not arrive in time for STM manufacture. |
| 5. Engineering Activities |
| Assembly of STM SCAL components |
| 6. Design Changes |
| None |
| 7. PA/QA Activities |
| PA database now in use |
| 8. Actions Requiring Immediate Attention |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones | Status |
| 5/12/00 | QMW source review | Complete |
| 22/05/01 | Calibrators design review (internal) | Complete |
| 18/12/02 | SCAL STM delivery to RAL | Est. del. 18/12/02 |
| 20/06/02 | CQM SCAL design review | Complete |
| 13/01/03 | CQM SCAL to RAL | Est. del. 13/01/03 |
| 18/10/02 | PFM calibrators design review | Rescheduled for late January 2003 |
| 01/10/03 | PFM SCAL to RAL | Late – due 09/12/03 |
| 03/01/05 | FS SCAL to RAL | Due 03/08/04 |
| 13. Schedule Changes |

Work Package	Filters

| 1. Subsystem Progress Since Project Inception |
| --- |
| SPIRE filtering scheme finalised. Prototyping in progress. Filter SSSD updated for DDR. Slight change of MW band for commonality with HFI band. |
| 2. Subsystem Progress This Month |
| SPIRE STM CFIL1 still in manufacture – delay due to long lead-time obtaining new photolithographic masters for CFIL1. STM PDIC1 and PDIC2 rings & shims still in manufacture – delay due to non-availability of SANMAC tube stock. Problem now solved, and manufacture started. STM PFIL2 and SFIL2 material ready for cutting to shape. 300mK spectrometer lenses complete. Assembly of SLW CQM filter/lens stack in progress. |
| 3. Problem Areas | Remedial Action |
| New photolithographic masters have been seriously delayed due to a supplier going into liquidation. A new supplier has now been sourced, and quotations have just been received. | If this continues to be a problem, and it looks like the delivery of the STM CFIL1 may hold up the STM schedule, Cardiff will supply a filter for STM tests only which has slightly reduced “active” area (i.e. that of our existing grids). |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| STM PDIC1 and PDIC2 rings & shims manufacture resumed after sourcing tube stock. |
| 6. Design Changes |
| Backup design of reduced active area CFIL1 complete |
| 7. PA/QA Activities |
| PA database now in use |
| 8. Actions Requiring Immediate Attention |
| 9. Status of Previous Actions |
| None |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones | Status |
| 18/09/01 | Filters DDR | Complete |
| 01/02/02 | STM 300mK filters to JPL | Complete – delivered 25/03/02 |
| 01/07/02 | STM input filters to RAL | Delayed - due 13/12/02 |
| TBD | CQM 300mK filters to JPL | Complete – delivered 12/09/02 |
| 13/01/03 | CQM filters to RAL | Due 13/01/03 |
| 03/02/03 | PFM 300mK filters to JPL | Due 03/02/03 |
| 01/08/03 | PFM filters to RAL | Due 01/08/03 |
| 03/02/03 | FS 300mK filters to JPL | Due 22/08/03 |
| 10/01/05 | FS filters to RAL | Due 29/12/03 |
| 13. Schedule Changes |
| Delivery dates currently under negotiation with RAL and JPL |

Work Package	300mK straps

| 1. Subsystem Progress Since Project Inception |
| --- |
| STM & CQM devices complete |
| 2. Subsystem Progress This Month |
| Electrical isolation joint concept thermal tests complete – report in progress. DM components re-assembled with higher Kevlar pre-load & sent to MSSL for mechanical characterisation. Photometer support performed well at random vibration levels in significant excess of SPIRE design levels. |
| 3. Problem Areas | Remedial Action |
| Evidence of wear on Kevlar in vicinity of radiused holes after vibration. (Light baffle only) | Polishing of all radiused holes is in progress to alleviate this problem. The polished light baffle will be sent to MSSL for re-test 15/11/02 |
| 4. Subsystem Management Issues |
| Ian Walker at Cardiff has assumed responsibility for the management of the 300mK strap program |
| 5. Engineering Activities |
| DM components re-assembled with higher pre-load for re-testing ay MSSL to verify FEA model |
| 6. Design Changes |
| None |
| 7. PA/QA Activities |
| None |
| 8. Actions Requiring Immediate Attention |
| Resolution of interface problem with structure. |
| 9. Status of Previous Actions |
| None |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones | Status |
| 7/6/02 | 300mK strap DDR | Date fixed |
| 20/11/02 TBD | STM 300mK straps to RAL |  |
| 13. Schedule Changes |
| Schedule under revision by Cardiff (managing 300mK programme) |

Work Package	AIV participation

| 1. Subsystem Progress Since Project Inception |
| --- |
| Cryogenic black body & flip mirror/shutter concept produced – approved at AIV review Conceptual design presented at AIV DDR. |
| 2. Subsystem Progress This Month |
| AIV filters submitted for manufacture Alternative supplier of large area photolithographic plates sourced (for filters), and order placed for quotation |
| 3. Problem Areas | Remedial Action |
| Delay in obtaining large photolithographic plates. | Alternative supplier sourced – quotation finally received 13/11/02 |
| 4. Subsystem Management Issues |
| Cardiff is no longer providing the AIV FTS |
| 5. Engineering Activities |
| none |
| 6. Design Changes |
| 7. PA/QA Activities |
| PA database now in use |
| 9. Actions Requiring Immediate Attention |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| Production of CBB & flip mirror module. Provision of reference detector Provision of FTS |
| 12. Budgets |
| 13. Milestones | Status |
| 31/5/02 31/5/02 TBD | CBB to RAL AIV Filters to RAL Reference detector to RAL | Due 31/01/03 Due 29/11/02 Due 31/01/03 |
| 14. Schedule Changes |

Work Package	JPL BDA test support

| 1. Subsystem Performance Progress Since Project Inception |
| --- |
| Optics modules designed manufactured Test cryostats at JPL Fridge #1 at JPL Fridge #2 at JPL Optics modules shipped |
| 2. Subsystem Progress This Month |
| Cryostat filters complete – due for shipping mid-November |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| Filters in production. |
| 6. Design Changes |
| 7. PA/QA Activities |
| None |
| 9. Actions Requiring Immediate Attention |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| To be defined |
| 12. Budgets |
| 13. Milestones | Status |
| 14. Schedule Changes |