Work Package:	Structure                                                           SPIRE-MSS-REP-001782

| 1. Subsystem Progress Since Project Inception |
| --- |
| Several concepts evaluated for the structure. Base line design decided upon in June 2000. Working on the system implications and implementation since first half of 2001. Continuing to close interfaces with the various subsystems. Started with production drawings in February 2001. The concept of the suspension has been analysed and decided on implementation. Hardware produced and tested, meets specifications. Detailed design continuing and manufacture is continuing. |
| 2. Subsystem Progress This Month |
| Thermal busbar development is continuing. A new schedule has been drawn up between Cardiff and MSSL. Production drawings of the busbar have been completed. Have tested MKIII units and light baffle from Cardiff and have started the FEA. The HOB simulator has arrived and the MGSE has been assembled. Production of the photometer 2K box spine has been completed but one of the batch was scrapped. The redesign of SCAL box has been confirmed and it has gone into production.* Spectrometer 2K Detector box has been scrapped at final inspection due to misalignment problems. Replacements have been started.* The manufacture of the Optical Bench was continuing.* Continuing to have integration team meetings with RAL, to address planning and integration issues. Released Issue 17 of the interface drawing. (* On Monday 28 October Thrust Engineering went into Liquidation. MSSL are currently working on a rescue plan to ensure that they have the remaining 3 parts for STM as soon as possible. The implications on the schedule are as yet unknown.) |
| 3. Problem Areas | Remedial Action |
| Also other subsystems have problems with them. Thermal busbar suspension has strong non-linear responses Level 1 thermal strap interface with spacecraft still has been confirmed Problems within the SCAL baffle box, forseen by the Optical team (LAM and RAL), have led to some redesign of the SCAL BOX Delivery date now 3 months late – due to additional work on thermal busbar and the scrapping of one set of optical benches. | Development team redefined the schedule for the project. Delivery date is mid-February Have produced design for the thermal bus bar itself . Received MKIII units from Cardiff. Finished mechanical characterisation tests and started FEA. Production design has been completed. The SCAL box design has been confirmed and is now in production. Constant monitoring of manufacturing progress and preplanning of follow on activities with RAL to minimise impact on whole project. |
| 4. Engineering Activities |
| FEA on thermal busbar. |
| 5. Design Changes |
| - |
| 6. PA/QA Activities |
| Preparation of End Item Data Package |
| 7. Subsystem Management Issues |
| - |
| 8. Actions Requiring Immediate Attention |
| - |
| 9. Status of Previous Actions |
| - |
| 10. Activities Yet to be Achieved |
| 11. Milestones | Status |
| February 2002 13-08-2002 01-02-2002 10-06-2003 01-10-2002 6-01-2004 | Interfaces defined and reported STM delivery to RAL CQM FTB enclosure to RAL PFM delivery to RAL PFM FTB enclosure to RAL FS delivery to RAL | Completed now 3 months late-15-11-02* On schedule On schedule On schedule |
| 13. Schedule Changes |
| Due to the thermal busbar design, manufacturing problems, and optical bench checking we are lagging 3 months behind on original schedule. |