Work Package:	BSM                                                                   SPIRE-ATC-REP-001788

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype tests complete. IBDR complete. Development Model testing |
| 2. Subsystem Progress This Month |
| DM-2 initial characterisation tests complete, investigative strip down and corrective mods completed. Tayco flexitapes received and re-build started. |
| 3. Problem Areas | Remedial Action |
| Full checks on repeatability/linearity in dewar to be achieved Launch Latch design Magnetic cross coupling | Scheduled for after Xmas. need to tie up with LAM. Detailed investigation, Mumetal screening, servo loop mods, cold tests, magnetic modelling |
| 4. Engineering Activities |
| Control loops closed up to the limit of (warm) motor saturation. Warm motor torque constants, repeatability and linearity tests performed and look good. A problem found with cross talk between jiggle and chop and poor unpowered repeatability on chop rest position also seen. Magnetic coupling between the chop and jiggle motors has been isolated as the cause of cross talk, and test data supports the hypothesis that the increase in spring rate (and maybe also unpowered repeatability) seen on the chop axis is due to coupling in of the jiggle spring rate by a stiff magnetic 'spring'. Discussions are progressing well with LAM on telemetry and BSM /MCU software. Discussions on the ICD with MMSL are in hand - some confusion over beam positions on the BSM. Launch latch ICD changes passed to LAM for comment. |
| 5. Design Changes |
| Minor design changes : the most significant being to add optical alignment tolerances to several assembly drawings in the light of DM-2 build experience. Given magnetic cross talk, we have issued a prototype mumetal shield design to the ATC workshop and will test this in January. The design has not been modelled and optimised, but works on the principle of placing the maximum amount of mumetal in the only conveniently available position. If tests are encouraging we will then optimise the design. |
| 6. PA/QA Activities |
| Progress on the update to the BSM SSSD slow due to ATC work loading, but good responses from RAL and LAM. Salvage machining to increase the range of chop travel completed. Investigative strip down of DM-2 revealed no major issues, although one motor package contaminated with Eccobond overspill from the jigged assembly process. Mumetal is now being considered for screening (already on the BSM declared materials lists against just this contingency). Discussed a change of screw lubrication regimes with RAL (ATC uses MoS2 but the Systems team would prefer the MSSL PFTE loaded apeizon grease scheme). |
| 7. Subsystem Management Issues |
| Given general DM-2 delays, the project schedule is being revised to ensure that deliverable models can still be released on time (to avoid a 2-4 month delay). There is a potential loss of knowledge transfer from DM-2, QM and CQM models in doing this, so it is being carefully reviewed. The milestone dates below assume we do adopt one of the proposed changes (plan 'C': releasing QM and PFM for manufacture before DM-2 tests are complete). Cost profiles are also being reviewed, and the SPIRE proposal that ESA procure the BSM directly is being considered. |
| 8. Actions Requiring Immediate Attention |
| MSSL (CBB) to advise screw torques for PFTE loaded apeizon grease CBB …. Ongoing ATC (IP) to confirm cold shake date for DM-2 … co-ordinating with RAL. End Jan03 favoured. |
| 9. Status of Previous Actions |
| SW11MAR02.02 IP Place contract for Zeiss motors … ongoing. |
| 10. Activities Yet to be Achieved |
| BSM SSSD update, BSM ICD u[date (launch latch, structure, MCU). Sign off of ATC PA plan. Improvements to the drawing configuration data base are being sought. |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| 20K test dewar available | N/A | Nov.02 | Dec02 | +1month |
| Integrate DM 2 at LAM | 30 Mar 01 | Nov.02 |  |  |
| DM release for manufacture | Oct.01 | Nov.01 | Dec.01 |  |
| DM-2 release for manufacture | N/A | Apr.02 | Apr.02 |  |
| 2 axis prototyping at ATC complete | N/A | Mar.02 | Apr.02 |  |
| SPIRE IBDR | N/A | Mar.02 | Mar.02 |  |
| DM-2 tests complete | 30.Apr 02 | 21.Mar.03 |  | + 2 months |
| BSM STM del'y to RAL | 01 Feb 00 | 5.Nov 02 | 5.Nov 02 |  |
| BSM CQM delivery to LAM | Jul.02 | Mar03 TBC |  | + 1 month |
| BSM CQM del'y to RAL | 13 Mar 02 | 26.May.03 |  | + 1 month |
| BSM QM tests complete (flight design valid) | 25.Apr.03 | 15.Aug.03 |  | +2 months |
| BSM PFM delivery to LAM | 03.Jun 03 | 15.Aug.03 |  | -1 month |