SPIRE IF Meeting Agenda, 18 November2003

From 09:00 to 17:30

Actions status:

See attached tables (4 pages)

IID-B issue 3.0 status

- Signature: SPIRE and ESA status

- Page 21 of Annex 5 “ HDD_1.1_Deltas Issue 2.pdf”

SPIRE general (or particular) technical status (TBD by SPIRE) :

- SPIRE schedule (if new inputs)

- Technical status (if new inputs)

Mechanical IF Issues:

- DRCU/QM & PSU/QM ICD’s, RFW 02

- SPIRE WU new ICD (issue 7) status

- JFET ICD status

- SPIRE Level-0 thermal strap IF:

- Status of new design

- Design of pump strap and integration issues

- Open pod evaporator IF

- Agreement of interfaces

- Status of FPU Support re-design

- Status of new design

- Availability of new FPU supports for MTD

- MGSE status:

- Design change of FPU MGSE: status

Thermal IF Issues:

- Agreement on thermal interfaces – Status after Instrument Thermal IF Mtg on 30/10/03

- Update of SPIRE Thermal Model: Next Release ?? (latest delivery date to ASED: 15 Jan. 2004)

- When are thermal conductance test data available from new supports?

Electrical IF Issues:

- Approval of SPIRE Cryo-Harness Data Package

- S/C SPIRE Scientific Harness design including pin-to-pin allocation

- Routing of SPIRE Scientific Harness

AIT Issues:

- AVM mechanical/electrical interfaces to be considered for the SVM simulator design (clarification of some specific points regarding the external power units)

- FPU testing during/after integration (which kind of EGSE will be used, what is the function of the warm units during these tests)

- (Thermal) background conditions for on-ground tests

Other:

- SPIRE CEA FM warm units (DCU & FCU) delivery date : answer to mail from BC ref H-P-ASP-LT-3868

- Procurement of JFET mounting hardware for MTDs (integration)

Minutes and actions, End of IF Meeting

SPIRE Actions Status

From last SPIRE Progress Telecon 29-10-03 , SCI-PT-21435

| N° | ACTION DESCRIPTION SCI-PT-21435 SPIRE Progress Telecon 29-10-03 | DUE DATE | Firm / person | ACTION STATUS |
| --- | --- | --- | --- | --- |
| 1 | SPIRE will assess the impact of late test results availability on the QM2/FM DRCU | 12/11 | SPIRE | Open |
| 2 | SPIRE will assess the scenario of the availability of warm units for FPU checkout after delivery to Astrium prior to cryostat enclosure. In addition SPIRE will issue a top-level document: - FPU/JFET integration procedure on the optical bench - Description of EGSE and/or WU needed for checkout. - Warm functional Tests to be performed prior cryostat enclosure. - Cold functional tests. | 30/11 | SPIRE | Open |
| 3 | SPIRE to issue the Harness Definition Document version 1.2, which will reflect HDD1.1 plus update according annex 5 of SPIRE IID-B version 3.0 “SPIRE HDD 1.1 Deltas” | 30/11 | SPIRE | Open |

SPIRE Actions Status

From last SPIRE IF&IIDB Meeting 4-09-03 , H-P-ASP-MN-3513

| N° | ACTION DESCRIPTION H-P-ASP-MN-3513 SPIRE IF&IIDB Meeting_4-09-03 | DUE DATE | Firm / person | ACTION STATUS |
| --- | --- | --- | --- | --- |
| 1 | SPIRE to issue an update of the FCU ICD, according to latest RFD (CR’s) with readable sizes | 30/9 | SPIRE J.D. | Open |
| 2 | Astrium will check if the change of altitude of the SPIRE JFET boxes can be taken into account (OBA, L3 interface position, and cryoharness (position of connectors). | 20/9 | Astrium. H.F. | Closed ? (Nearly closed by fax HP-ASED-FX-0749-03 dated 19/09/03, and HPLM PM17 minutes HP-ASP-MN-3704 29/09/03) |
| 3 | In case the change can be implemented (AI 2 output), SPIRE will issue a CR | 30/9 | SPIRE J.D. | Open |
| 4 | SPIRE to add AVM ICD’s (in case they are different from FM’s) in the next IID annex pack | 30/9 | SPIRE J.D. | Open |
| 5 | Astrium & RAL will agree on a suitable descriptive text to be implemented in IID-B ch 5.10 for harness-overshield (red line modification, no CR required) | 10/9 | SPIRE JD | Closed (by IIDB v 3.0) |
| 6 | Alcatel will check that this spare LCL can be made available to SPIRE | 10/9 | Alcatel GD | Closed - Mail Keithrobert Hibberd « LCL Loan » 15/09/03. Waiting for SPIRE answer |
| 7 | Use of “force limited vibration testing” implies automatic notching (random vibration). Input levels actually applied to the instrument should be sent to ESA/Alcatel for agreement | 15/9 | SPIRE/MSSL | Closed – Mail E.Sawyer 29/10 with “Instrument Vibration Test Report 1.0.pdf” |
| 8 | ESA to check and comment the SPIRE EIDP content list | 15/9 | ESA J.R. | Open |
| 9 | SPIRE to check that all AD/RD documents are on livelink. | 15/9 | SPIRE JD | Open |
| 10 | SPIRE to provide TN with definition of safing plugs that are needed | 30/9 | SPIRE JD | Open |
| 11 | Astrium will make a detail evaluation of the conduction / Dissipation (discriminate between both) of the SPIRE cryoharness to the FPU. (this could mean using electrical resistance at operating temperature). | 19/9 | Astrium A.H | Open |
| 12 | Annex 4 describing the thermal behaviour of the sorption cooler will be sent by SPIRE | 10/9 | SPIRE JD | Closed – Annex 4 is in IIDB v3.0 draft 1 |

From Previous Meetings ACTION ITEM LIST STATUS 1/2

| N° | ACTION DESCRIPTION | DUE date | Resp | Status |
| --- | --- | --- | --- | --- |
|  | From HP-ASPI-MN-3310 (26/06/03) |  |  |  |
| 01 | SPIRE to issue a CR providing text/inputs for all sections & sub-sections of IIDB concerned by AIV, Testing, Verification, Hardware matrix and model philosophy | 26/09/03 | SPIRE | Still Open - New date: End sept 03 |
| 02 | ASED to provide SPIRE the Step files of relevant OB assembly | 15/07/03 | ASED | Closed: HP-ASED-EM-0443-03 |
| 03 | SPIRE to provide inputs: Performance of Sorption Cooler with shunt strap connected to the pump heat switch Detailed heat loss budget on 300mK strap Visibility of SPIRE level 0 strap (between thermal I/F and FPU) including margins, materials, … | 26/09/03 | SPIRE | Closed ? by Thermal meeting H-P-ASP-MN-3923 |
|  | From HP-ASPI-MN-3081 (06/05/03) |  |  |  |
| 02 | SPIRE comments on doc: HP-2-ASED-TN-0002 Alignment Plan-Concept / Herschel (AD 7 of IIDB) | 30/05/03 | SPIRE | Closed – No comments |
| 05 | SPIRE to provide Courage and Cristek connectors data | 30/05/03 | SPIRE | Closed - Obsolete |
| 08 | ASED to verify the 50 mA capability of harness | 16/05/03 | ASED | Closed (mail H.Fass 03/07/03) Ref. HP-ASED-EM-0365-03 |
| X | SPIRE Inputs & comments on IIDB 2.3 draft 2 to 4 (see AI 3 MN-2748) | 16/05/03 | SPIRE | Closed - Obsolete |
| X | ASED Inputs & comments on IIDB 2.3 draft 2 to 4 (see AI 3 MN-2748) | 16/05/03 | ASED | Closed - Obsolete |
| X | ALS Inputs & comments on IIDB 2.3 draft 2 to 4 | 16/05/03 | ALS | Closed - Obsolete |

From Previous Meetings ACTION ITEM LIST STATUS 2/2

| N° | ACTION DESCRIPTION | DUE date | Resp | Status |
| --- | --- | --- | --- | --- |
|  | From HP-ASPI-MN-2298 (26-27/11/02) |  |  |  |
| AI 2 | Update IID-B: §5.16: Add hardware matrix (deliverable items) ; §9: to provide input wrt testing & verification ; § 5: details of all points of electrical isolation on SPIRE FPU & JFETs (by new ECR 53) | SPIRE | 30/05/03 | Closed - Obsolete |
|  | From HP-ASPI-MN-2748 (27/2/03) |  |  |  |
| AI 9 | Integration procedure of FPU on Optical bench | SPIRE | 30/10/03 | Still Open - moved to end October 2003 |
|  | From ASED |  |  |  |
|  | From HP-2-ASED-MN-0182 |  |  |  |
| AI 8a | HP-2-ASED-MN-0182 MSSL / BW should clarify how the SPIRE red tagged cover should be respresented in the IF drawings | MSSL | 30/06/03 | Closed |
| AI 3 | RAL/JD to evaluate the L0 interface and its implications on L0 instrument side design | SPIRE | 10/07/03 | Closed - Deleted |
|  | From HP-2-ASED-MN-0387. AIV meeting. |  |  |  |
| 5 | Thermal environment during IST-IMT | SPIRE |  | Still Open |
| 8 | most sensitive noises mode. Will be Identified in test sheet. | SPIRE |  | Still Open |
| 11 | Define power lines to be tested | SPIRE |  | Still Open |