SPIRE Actions Status

From last SPIRE IF Meeting 10-02-04 , H-P-ASP-MN-4307

| N° | ACTION DESCRIPTION H-P-ASP-MN-4307 SPIRE IF Meeting 10-02-04 | DUE DATE | Firm / person | ACTION STATUS |
| --- | --- | --- | --- | --- |
| 1 | Redundant connectors position on DCU/FCU QM1 should be included on CR 64/65 in a version 2 of the CR 64/65. | 20/02/04 | SPIRE | Open |
| 2 | SPIRE to reply to list of open points from Alcatel CCB included in Annex 1-2/3 | 27/02/04 | SPIRE | Open |
| 3 | ESA to sort out the problem of availability of DRCU CQM 1 between HPLM EQM test & SPIRE FM test (summer/Automn 2004) | 03/03/04 | ESA | Open |
| 4 | SPIRE to issue a CR with update of the FPU ICD to version 19 | 27/02/04 | SPIRE | Open (partially closed by Pack issue 10 received 26/02, but without CR) |
| 5 | ASED to update the harness shield definition according to the clarification during the meeting. | 17/2/04 | ASED | Open |
| 6 | SPIRE to issue a CR if they want to increase the BSM motors currents from 40 to 60mA, and to investigate alternative solution (internal to SPIRE) | 27/02/04 | SPIRE | Open |
| 7 | Action to ASED to cross check that the currents which are used to design cables (ref IID-A 3.1 annex 8 tables) are compliant with the one in the HDD 1.1 + annexes in IID-B 3.11 | 27/02/04 | ASED | Closed by HP-ASED-FX-0096-04 dated 13/02/04 with attached mails dated 12/02/04 and 16/02/04 |
| 8 | SPIRE to update the integration procedure according to the ASED redlined version in annex 5 |  | SPIRE | Open |
| 9 | It should be checked again if this vacuum grease can be used to avoid cold welding, of find an alternative for lubricating the screws. | 27/02/04 | ASED | Open |
| 10 | DCU/FCU model philosophy (QM2/FM) needs to be formalised . SPIRE will issue a RFW to formalise this situation | 27/02/04 | SPIRE | Open |

From  previous SPIRE IF Meetings (only open AI)

| N° | ACTION DESCRIPTION H-P-ASP-MN-3961 SPIRE IF Meeting 18-11-03 | DUE DATE | Firm / person | ACTION STATUS |
| --- | --- | --- | --- | --- |
| 2 | Alcatel ask SPIRE to prepare a list of expected interface changes wrt current IID-B 3.0 baseline definition, to be discussed during next interface meetings | 30/11 | SPIRE | Open– new date 27/02/04 |
| 3 | Astrium will evaluate how the termination of the cryoharness can be done in compliance with EMC test objectives (for instance terminating the unused cryoharness at the SVM bracket. | 15/12 | ASED | Closed ? by Fax HP-ASED-FX-0055-04 dated 03/02/04, stating baseline is: EQM identical to FM for units and harness, no specific EMC measure |
| 9 | SPIRE/MSSL will provide MGSE ICD by mid 01/04 | 15/01/04 | SPIRE/MSSL | Open New date 27/ 02/04 |

| N° | ACTION DESCRIPTION H-P-ASP-MN-3513 SPIRE IF&IIDB Meeting_4-09-03 | DUE DATE | Firm / person | ACTION STATUS |
| --- | --- | --- | --- | --- |
| 11 | Astrium will make a detail evaluation of the conduction / Dissipation (discriminate between both) of the SPIRE cryoharness to the FPU. (this could mean using electrical resistance at operating temperature). | 15/12 | Astrium A.H | Open new date = issue of the document for CDR (april 04) |

| N° | ACTION DESCRIPTION | DUE DATE | Firm | ACTION STATUS |
| --- | --- | --- | --- | --- |
|  | From HP-2-ASED-MN-0387. AIV meeting. |  |  |  |
| 5 | Thermal environment during IST-IMT. Worst T environment to still be able to test the cooler in the cryostat vs L0 and L1 temperatures | 12/11/03 | SPIRE | Still Open – Answer of SPIRE is that Instrument cannot be tested with proposed temperature environment (7K on level 1). No Cooler recycling possible. SPIRE will run the model and provide a feed-back. New due date: 15/03/04 |
| 8 | most sensitive noises mode. Will be Identified in test sheet. | 15/12/03 | SPIRE | Still Open– Will be included in SPIRE TN 982 “SPIRE EQM test program definition” to be updated . New due date 13/02/04 |
| 11 | Define power lines to be tested | 15/12/03 | SPIRE | Still Open– Idem AI 8 |

from SPIRE Progress Telecon’s

| N° | ACTION DESCRIPTION Progress Telecon # | DUE DATE | Firm / person | ACTION STATUS |
| --- | --- | --- | --- | --- |
|  | SCI-PT-21435 SPIRE Progress Telecon #2_ 29-10-03 |  |  |  |
| 3 | SPIRE to issue the Harness Definition Document version 1.2, which will reflect HDD1.1 plus update according annex 5 of SPIRE IID-B version 3.0 “SPIRE HDD 1.1 Deltas” | 30/11 | SPIRE | Open Problem of availability. Patches in IID-B are equivalent (HDD 1.1 + patch v.3 (tech not v3.0 should be replaced in IID-B). Keep open. |