# Introduction

At the last Co-Is meeting I was asked to consider ways of organising the ICC development work in such a way as to define as far as possible a set of workpackages each of which could be assigned to a single individual or institute on the understanding that it would be easier to provide and manage resources to participate in provision of a easily identified workpackage rather than contribute to the work of joint development teams. This document attempts to define such a set of workpackages, although some (coordination) activities will clearly have to be carried out by a team of representatives from several institutes – in these cases I have nominated the appropriate team leader as responsible.

This first version of the note makes no allocation of workpackages to institutes known to want to be involved in development of the ICC. This will be the subject for discussion at the Consortium Meeting in October.

# Workpackages

## General

This way of splitting the work will only operate effectively if workpackages are made the responsibility of a single institution, with a clearly identified manager, who has the authority to control the resources available to meet the required deliveries and milestones. Each manager will have to prepare a plan, including schedule, for providing the required outputs and meeting the required deadlines. These managers should be identified at the time that the workpackage is accepted.

The manager will be responsible for reporting progress to the ICC Development Manager

## Data processing Workpackages

The main workpackages concern the processing of data from scientific observations and is based on the data processing steps identified by Tanya during her investigation of the calibration files required for processing SPIRE data. These may need to be modified as a better understanding of the SPIRE Observing modes becomes available.

For information the Data Flow diagrams observation data processing are attached at the end of the document.

Table 1 shows the data processing steps identified in Tanya’s Data Flow Diagrams. These are grouped into workpackages containing a set of related processing steps and identifies the calibration files associated with each workpackage.

# Table 1:  Data Processing Workpackages

| Responsible | WP Title | Processing Steps | Calibration Files |
| --- | --- | --- | --- |
| RAL | Engineering Data | Apply Bad Pixel Mask Convert to Digital Units Correct for Offsets and Gains Extract HK data | Bad Pixel Mask Conversion Tables |
|  | Detector Response | Determine Relative Response Apply Relative Response Correction Determine Absolute Responsivity Correction Apply Absolute Responsivity Correction | Photometric Cal File Detector Cal File |
|  | BSM | Assign Chop Position to Detector Timeline Assign Jiggle position to Detector Timeline Demodulation |  |
|  | Averaging | Statistical Deglitching Average Data |  |
|  | Degitching | Deglitching |  |
|  | Pointing | Assign S/C pointing to Detector Timeline Correct for Telescope pointing drift Absolute pointing reconstruction Assign Nod Position to new timeline Flag Telescope turn around period | Bolometer Array Offsets File |
|  | Flat field | Correct for Electrical Crosstalk Correct for Optical Crosstalk Apply Flat Field Correction | Electrical Crosstalk File Optical Crosstalk File Flat Field Cal File |
|  | Fourier Transform | Convert from Encoder Posn to Mechanical Posn Convert from Mechanical Posn to OPD Regrid interferogram Phase Correct Fourier Transform | Position Cal File OPD Cal file ZPD for each Detector |
|  | SCAL | Correct for Drift in SCAL output |  |
|  | Telescope | Correct for Drift in telescope Background Remove Telescope Emission (TBC) |  |
|  | Spectral Response | Correct for Time dependency in Spectral Response Correct for Spectral Response | Time S/R Cal file Spectral Response File |
|  | User Products | Avarage Spectra Convert to Watts Colour Correction Change units to Janskys Determine Source Signal and position | Conversion Calibration File Spectral Response or Colour Correction Cal File Conversion Factors mJy/Str PSF |

In essence each workpackage contains the same set of activities associated with a set of data processing steps. These include:

- Definition of the input/output data products

- Definition of the required calibration information

- Checking that the Calibration Plan provides the calibration information

- Analysis of calibration test data to produce the required calibration information

- Specification of the Data processing Steps based on the agreed observing mode definitions

- Development/Coding of the Data Processing Steps in the IA environment, including

  - the provision of test data

  - software for generating quality information

  - software for deriving long term trend data products

- Participation in the CALT, OBST and ISDT in their coordinating roles

The workpackages have been limited to those associated with providing the reduced set of Data Products identified at various meetings as the minimum set which will allow the general observer to start scientific analysis.

# Workpackage Summary

Currently only the workpackages for the Development Phase have been addressed

ICC Development Work Packages Summary

| Continuous Tasks |
| --- |
| WP No | Title | Responsible |
| GHS11X1100 | Overall ICC Management Activities | RAL |
| GHS11X3000 | Product / Quality Assurance | RAL |
| GHS11X2000 | ICC System Engineering | RAL |
| GHS11X4000 | Herschel Ground Segment Development | RAL |
| GHS11X5000 | ICC Operations during Development | all |
| GHS11X6000 | Information dissemination | all |
| GHS13X2000 | ICC Design | all |
|  | Training | all |
|  | Observations and Science Data Reduction Team | ICSTM |
|  | Operations Team | RAL |
|  | ICC Software Development Team | RAL |
|  | Calibration Team | CEA |

| Generation of Instrument Information |
| --- |
| WP No | Title | Responsible |
|  | Instrument Users Manual | RAL |
|  | Instrument Observations | OBST |
|  | Ground Testing of Instrument Observations | RAL |
|  | Simulation of Instrument Observations |  |
|  | Time Estimator |  |

| ICC Development |
| --- |
| WP No | Title | Responsible |
| GHS13X1100 | SPIRE Contribution to the HCSS | ISDT |
| GHS13X3000 | Software Development Infrastructure | RAL |
| GHS13X5000 | Quick-Look Analysis | ISDT |
| Data Processing |
|  | IA Development System | RAL |
|  | IA Access Tools | RAL |
|  | Engineering Data | RAL |
|  | Detector Response |  |
|  | BSM |  |
|  | Averaging |  |
|  | Deglitching |  |
|  | Pointing |  |
|  | Flat Fielding |  |
|  | Fourier Transformation |  |
|  | SCAL |  |
|  | Telescope |  |
|  | Spectral Response |  |
|  | User Products |  |
| I/F only | Scan Mapping |  |
| GHS13XB000 | Quality Control ‘Pipeline’ |  |
|  | Photometric Data Analysis |  |
|  | Spectrometric Data Analysis |  |
| Not Funded | Instrument Simulator |  |
| Not Funded | Provision of Serendipity Mode Processing Software |  |
| Not Funded | Key Programs |  |

| Support to Instrument Team Activities |
| --- |
| WP No | Title | Responsible |
| GHS21 | ILT Support |  |
| GHS21X1000 | Provision of ILT System(s) – includes integration of ILT systems |  |
| GHS21X2000 | Produce validation software to validate scripts and observation requests |  |
| GHS21X3000 | Produce Command Validator |  |
| GHS21X4000 | Populate Calibration Database (ILT data) |  |
| GHS21X5000 | Support to ILT Tests |  |
| GHS22 | IST Support |  |
| GHS22X1000 | Provision of IST System(s) |  |
| GHS22X2000 | Populate Calibration Database (IST data) |  |
| GHS22X3000 | Support to IST Tests |  |

| ICC Operations Preparation |
| --- |
| WP No | Title | Responsible |
| GHS31 | Facilities |  |
| GHS31X1000 | ICC Operations Centre |  |
| GHS31X2000 | DAPSAS (UK) Centre |  |
| GHS31X3000 | DAPSAS (Fr) Centre |  |
| GHS33 | Integration and Test |  |
| GHS33X1000 | ICC Integration |  |
| GHS33X2000 | Ground Segment Integration |  |
| GHS33X3000 | Ground Segment Testing |  |
| GHS34 | Commissioning Phase |  |
| GHS34X1000 | Provision of Commissioning Phase System (ICC@MOC) |  |
| GHS34X2000 | Commissioning Phase Support |  |

| WP Title: Overall ICC Management Activities | WP Number | GHS11X1100 |
| --- | --- | --- |
|  | Version: | 1.2 |
| WP Manager: ICC Development Manager | Date: | 24 Sep 03 |
| Description: This workpackage covers those activities related to overall management of the design and development of the SPIRE ICC and management of those activities specific to the Operations Centre |
| Start Date: | End Date: | Type: Continuous |
| Inputs: Development Plans from other centres Reports from other centres Contributions to SIP |
| Activities: ICC Development Planning, including SIP Provision Organisation of ICC Definition Team Meetings Reporting to ICC Steering Group Progress reporting to SPIRE Project on ICC development activities Progress reporting to Herschel Project on ICC development activities Organisation and support to SPIRE ICC Reviews Support to Herschel Ground Segment Reviews ICC Project Control and Schedule Management |
| Outputs: SPIRE SIP Progress Reports to SPIRE Project Progress Reports to Herschel Project |
| Assumptions: The facilities of the SPIRE Project Office are available for use by the ICC. Livelink will be used for all documentation and administration of this system is outside the scope of this workpackage (and the ICC, during the Development Phase) |
| Notes: |
| Resources: |

| WP Title: Product / Quality Assurance | WP Number | GHS11X3000 |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: ICC PA Manager | Date: | 10 Jan 2001 |
| Description: This workpackage covers all PA/QA activities associated with the ICC in the Development Phase |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: Provision of ICC Hardware and Software PA/QA Plans Operation of the Configuration Control System (SPR/NCR) for ICC Software development Operation of the Configuration Control System (NCR) for ICC systems development Configuration Control of On Board Software after delivery from IFSI Acceptance of Delivered systems for ICC Liaison with ESA PA Section |
| Outputs: ICC PA Plan ICC Software PA Plan |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: ICC System Engineering | WP Number | GHS11X2000 |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: ICC Systems Engineer | Date: | 10 Jan. 2002 |
| Description: This workpackage covers all system engineering activities associated with the ICC |
| Start Date: | End Date: | Type: Continuous |
| Inputs: SPIRE Operating Modes Document SPIRE Operations Scenario Document |
| Activities: Definition of Instrument Operations - breakdown to instrument command level Definition of Instrument Data Interface with the spacecraft Definition of SPIRE Operating Procedures Definition of SPIRE Autonomy/Safety Concept Definition of ICC Internal Interfaces Definition of SPIRE ICC Operating Procedures Definition of ICC Testing |
| Outputs: Operating The SPIRE Instrument Document SPIRE Data Interface Control Document SPIRE Operations Document SPIRE Autonomy/Safety Document SPIRE ICC Interfaces Document SPIRE ICC Operating Procedures Document SPIRE ICC Test Plan SPIRE ICC End-to-End Test Plan |
| Assumptions: |
| Notes: System Engineering activities related to the interface to the FSC are contained in other workpackages |
| Resources: |

| WP Title: Herschel Ground Segment Development | WP Number | GHS11X4000 |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 10 Jan. 2002 |
| Description: This workpackage covers all management activities concerned with development and design of the Herschel Ground Segment, including both interactions with ESA and the other Herschel instrument groups. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: HGSAG Activities HCSSMG Activities HGS System Engineering Liaison with HSC Development Manager Liaison with ICC Development Managers Monthly progress reporting for SPIRE HCSS development activities Support to Ground Segment Reviews |
| Outputs: Monthly Development Progress Reports |
| Assumptions: |
| Notes: Work related to software development and design is included in the relevant workpackages elsewhere |
| Resources: |

| WP Title: ICC Operations during Development | WP Number | GHS11X5000 |
| --- | --- | --- |
|  | Version: | 1.1 |
| WP Manager: | Date: | 24 Sep. 2003 |
| Description: This workpackage covers all activities concerned with operating ICC facilities during the Development Phase. As ICC systems are developed, purchased, or supplied, they will be operated and maintained as part of the ICC by the relevant centres. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: Computer Systems procurement, installation and maintenance, including software licences Defining and Operating procedures for control of access to HSC/ICC systems Operation of ICC Help Desk (TBC) General software maintenance activities for systems that do not have a specific maintenance work package. |
| Outputs: |
| Assumptions: The SPIRE Project Office will handle all day-to-day organisation and administrative duties |
| Notes: For convenience, all recurrent costs (Telephone, Teleconference, Video Conference, consumables) are accumulated under this Workpackage This includes: Software Licensing, Hardware maintenance costs, Publicity materials |
| Resources: |

| WP Title: Information dissemination | WP Number | GHS11X6000 |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 10 Jan. 2002 |
| Description: This workpackage covers all activities concerned with the dissemination of information to the consortium, astronomers and the general public. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: ICC Web page design and Maintenance Provision of Publicity material Participation in Press conferences Support to PPARC publicity events Maintenance of mail/email distribution lists Participation in Consortium meetings |
| Outputs: Press Releases Publicity Material |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: ICC Design | WP Number | GHS13X2000 |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 10 Jan. 2002 |
| Description: This workpackage covers all activities concerned with the design of the ICC itself |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: The ICC will be designed and developed following an object–oriented methodology employing the following steps: Definition of ICC User Requirements Definition of ICC Conceptual Model and Operations Scenario(s) Definition if ICC Use Cases Definition of ICC Workpackages Definition of Internal ICC interfaces Provision of Design documentation |
| Outputs: ICC User Requirements Conceptual Model and Operations Scenario(s) ICC Use Cases ICC Workpackages Internal ICC interfaces Design documentation |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Training | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 10 Jan. 2002 |
| Description: This workpackage covers all training activities in the ICC. It is the responsibility of each group participating in the ICC to provide suitable training for their staff |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: This is the high-level summary workpackage covering ICC training activities throughout the ICC Development Phase: Training in the use of HCSS systems – CUS, MPS, Scheduling Training in the use of external systems – MIB Editor, SCOS2000 Other training – programming languages, Operating systems, databases |
| Outputs: |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Observations and Science Data Reduction Team | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: OBST Leader | Date: | 24 Sep. 2003 |
| Description: This workpackage covers activities concerned with the management of the activities of the OBST as defined in the WP ‘Instrument Observations’ |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: Plan/Control and manage the activities of the OBST Organising and run meetings of the OBST Report on OBST Activities |
| Outputs: Minutes of Meetings OBST Reports |
| Assumptions: |
| Notes: Participation in the work of the team is covered by individual Data Processing workpackages and the Instrument Observations workpackage. This WP covers the extra tasks and responsibilities of the team leader. |
| Resources: |

| WP Title: Operations Team | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: OPST Leader | Date: | 24 Sep. 2003 |
| Description: This workpackage covers all activities concerned with verifying the operational modes of the instrument and calibration testing and setting up and integrating the ICC for operations |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: Provision of MIB, CUS and other instrument databases necessary to implement the instrument operational modes, including observations and building blocks Specification of tests (on the ground and during the Commissioning Phase) to verify correct operation of the instrument in all its operating modes Provision of scripts (Test Control, TOPE, QLA etc) to perform calibration and observation verification tests Analysis of data from tests to verify the correct operation of the instrument in its operating modes Specification and Development of software to process instrument engineering data to monitor the continuing health and performance of the instrument Specification of date processing steps for instrument monitoring during the operations phase Definition of operating procedures and provision of an Operations Plan Installation and test of externally provided systems (SCOS, MIB editor, HCSS, IA) Definition and execution of ICC integration Tests and Herschel Ground Segment Tests Provision of all ICC infrastructure (hardware) and installation of software for use by ICC teams for analysis of test data and for use during the Operations Phase Provision of training for users of ICC Systems Setup of the instrument Cryogenic Test Facility for use during Operations Setup and Training of the Operations Team for the Operations Phase Training of ICC-external users in ICC software and systems Plan/Control and manage the activities of the OPST Report on OPST Activities |
| Outputs: MIB and CUS databases Test Specifications Test scripts Test Reports Operations Plan OPST Reports |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: ICC Software Development Team | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: ISDT Leader | Date: | 24 Sep. 2003 |
| Description: This workpackage covers all activities concerned with coordination of software development activities in the ICC. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: Coordination of QLA softwar edevelopment Provision of QLA software Provision of QLA documentation (UsersGuide etc) Coordination of IA data processing software development Provision of SPIRE IA software Provision of IA Documentation (Users Guide, Installation Manual, Data Products Definition etc) Support to delivery/installation and test of SPIRE IA Software Plan, Control and Manage the activities of the ISDT Report on ISDT Activities |
| Outputs: Minutes of Meetings ISDT Reports |
| Assumptions: |
| Notes: Most of the work of the team is covered by individual software development workpackages. This WP covers the extra tasks of the team with respect to delivery of QLA and IA |
| Resources: |

| WP Title: Calibration Team | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: CALT Leader | Date: | 24 Sep. 2003 |
| Description: This team is responsible for defining the calibration plan for the instrument, coordinating activities associated with obtaining the required data and analysing it. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: |
| Activities: Definition of the SPIRE Calibration Plan (Ground and Flight) Specification of calibration ground tests Coordination of analysis of data from ground calibration tests held at instrument-level Definition of the calibration database Population of the calibration database from ground testing and other facilities (subsystem tests, other telescopes, literature) Coordination of IA data processing modules for calibration data processing Definition of calibration processing procedures Plan/Control and manage the activities of the CALT Report on CALT Activities |
| Outputs: Calibration Plan Calibration Database Calibration Processing Procedures CALT Reports |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Instrument Users Manual | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep. 2003 |
| Description: The Instrument Users Manual is a document delivered to ESA, which describes all aspects of the instrument design and behaviour. The SPIRE instrument manual will be delivered in two parts: the manual itself, being as far as possible, extracts from existing SPIRE documentation plus operating procedures taken from the AIV activities; and a SCOS2000 database (MIB) containing definitions of the instrument commands and telemetry. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: OIRD – contains a table of contents for the IUM Selected SPIRE documentation SPIRE Operating procedures |
| Activities: Negotiate contents of IUM Compile IUM from extracted data from SPIRE documentation and AIV Procedures |
| Outputs: April 2004: IUM Version1 (CQM/AVM) – delivered with CQM/AVM June 2005: IUM Version 2 (PFM) – delivered with PFM June 2006: IUM Version 3 (Flight) MIB for testing purposes – as needed |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Instrument Observations | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: OBST Team Leader | Date: | 24 Sep. 2003 |
| Description: This workpackage covers all activities concerned with end-to-end specification and verification of the instrument observations and their data products. This will require coordination and discussion with all parts of the consortium and with ESA to ensure the optimum use of the instrument and Herschel satellite. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: Simulated data for Observing modes |
| Activities: Specification of the AOTs, their input parameters as seen by the observer, the logic for translating these into a series of instrument building blocks. Specification of the building blocks in detail (e.g. chop size/frequency, FTS scan lengths/speed, calibration. operations). This will require simulation of expected observation data as well as testing of building blocks with the instrument – see other WPs Specification of the data products from each observation type Specification of the required data processing steps to reduce data from observations into the data products. (The Algorithms used are the responsibility of the s/w writers) Coordination with the HSC and other instruments to ensure compatibility of the observations, processing and data products across the Herschel instruments. Preparation of Verification Plans for Ground and In-Flight (Commissioning and PV Phase) to verify the different observational modes and data processing software Generation of observations to implement the Ground and In-Flight Verification Processing and Analysis of Ground Verification observation data Provision of initial data processing procedures (‘pipeline’) for standard reduction of observation data Provision of the SPIRE Observer’s Manual and additional documentation required for informed used of the instrument |
| Outputs: April 2004: AOT Specifications April 2004: Building Block Specifications September 2004: Data Processing Step Specifications January 2005: Ground Observation Verification Plan January 2005: Observers Documentation January 2006: Ground Verification observations June 2006: In-flight Observation Verification Plan June 2006: In-flight Verification observations June 2006: Standard Data Processing Pipeline definition |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Ground Testing of Instrument Observations | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep. 2003 |
| Description: This workpackage covers activities associated with testing instrument observation modes and the building blocks that are used to create them. This information is used to select the correct way to implement building blocks and their use in observations |
| Start Date: | End Date: | Type: Continuous |
| Inputs: April 2004: Building Block Specifications April 2004: Observation mode specifications |
| Activities: Generation of building blocks and observations in the CUS to represent the specifications Specification of tests to verify the building blocks and observations Execution of the tests to verify the building blocks and observations Analysis of the data from tests |
| Outputs: July 2004: Test Reports December 2004: Test Data for use in testing processing steps |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Simulation of Instrument Observations | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep. 2003 |
| Description: This workpackage covers activities associated with simulating the affect of different building block specifications (e.g. FTS scan speed, chopping frequency etc) on the data that is produced by the instrument. This information is used to select the correct way to implement building blocks and their use in observations. |
| Start Date: | End Date: | Type: Continuous |
| Inputs: April 2004: Building Block Specifications April 2004: Observation mode specifications |
| Activities: Simulation of the data from specified building blocks Analysis of the data |
| Outputs: Test Reports December 2004: Simulated Data for use in testing processing steps |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Time Estimator | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep. 2003 |
| Description: The time estimator is required to allow observers to check the feasibility of observations and to optimise proposal inputs. There are two versions of the time estimator required; the first is a simple algorithm for estimating the total time of an observation. This will be put into the observers manual and be used by observers to plan proposal submission; the second time estimator will be part of the proposal input system and will give observers an accurate estimate of the time of each observation they enter. It Is not clear how much work this second TE will incur as the proposal input tool interfaces to the CUS, which should be able to provide accurate times for command sequences. The only task will then be too provide information on the way in which observers input is translated into command sequences . |
| Start Date: | End Date: | Type: Continuous |
| Inputs: SPIRE Observation and Building Block Specifications |
| Activities: Determination of an algorithm for determining the time of an observation Provision of information to allow translation of observers input parameters into command sequences Provision of additional software required for time estimation (TBC) |
| Outputs: Time Estimator algorithm Time Estimator software (TBD) |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: SPIRE Contribution to the HCSS | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: ISDT Leader | Date: | 24 Sep. 2003 |
| Description: This workpackage covers the contribution made by SPIRE to the development of the HCSS and IA |
| Start Date: | End Date: | Type: Continuous |
| Inputs: HCSS System Software Project Management Plan |
| Activities: Participation in CSDT meetings Participation in IA/QLA working group meetings Participation in HCSS and IA Reviews Software development of specific modules Documentation |
| Outputs: HCSS and IA software modules HCSS and IA documentation |
| Assumptions: |
| Notes: |
| Resources: |

| WP Title: Software Development Infrastructure | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: Provision of system(s) necessary to allow software development in a controlled manner This includes provision of a problem reporting system, a version control system, and management of their use. |
| Start Date: | End Date: | Type: |
| Inputs: SPIRE Configuration Management Plan |
| Activities: Provision of a system for storage and version control of software code Provision of a system for software problem reporting and management Configuration control of software development and releases (including running Configuration Control Board meetings) |
| Outputs: Software Version Control system Software Problem Reporting system Procedures for use of the systems CCB meeting minutes |
| Assumptions: The ESA SPR system and CVS server will be available for use by the ICC. |
| Milestones: Jan 2003: Version Control system available Jan 2003: Software Problem Reporting system available |
| Notes: This WP will make use of much of the HCSS development infrastructure. Only the extra effort to configure it for use by the ICC and for running the CCB are covered by this WP |
| Resources: |

| WP Title: Quick-Look Analysis | WP Number | GHS13X5000 |
| --- | --- | --- |
|  | Version: | 1.2 |
| WP Manager: | Date: | 24 Sep 2002 |
| Description: This work package covers the development of the Quick-look Analysis (QLA) software. Several versions will be required for use with different instrument Models. |
| Start Date: July 2001 | End Date: July 2007 | Type: |
| Inputs: |
| Activities: Requirements definition Analysis and design Implementation Maintenance Participation in ICC Software Development Team (ISDT) meetings |
| Outputs: QLA Requirements Document June 2003: QLA Version 1.0 (AVM) October 2003: QLA Version 2.0 (CQM) June 2004: QLA Version 3.0 (FM) June 2006: QLA Version 4.0 (Flight) |
| Assumptions: QLA is outside the scope of the HCSS, though it will make use of it. QLA will attempt to use functionality provided as part of the common IA framework |
| Notes: The versions correspond to milestones. It is envisaged that development will be an incremental one with other versions between milestones as new features are added. |
| Resources: |

| WP Title: IA Development System | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: Provision of a system to allow development of IA processing steps. This involved adaption of the common IA working group output to SPIRE requirements |
| Start Date: | End Date: | Type: |
| Inputs: HCSS and IA framework produced by Herschel common development teams Test Data from ground testing or simulation |
| Activities: Provision of IA Development System hardware Installation of HCSS and IA framework on IA Development System Maintenance of the IA Development System (Updates to hardware and software) System Management of the IA Development System Provision of Stand-Alone IA Provision of documentation for using the Stand-Alone IA System Installation of Test Data on the IA Development System (produced by simulation or from ground testing) |
| Outputs: IA Development system containing Test Data Stand-Alone IA Software SPIRE Stand-Alone IA Installation Guide SPIRE IA Programmers and User Guides SPIRE Software development guidelines (coding standards, GUI characteristics etc) |
| Assumptions: HCSS and IA framework are available in the Spring of 2004 |
| Milestones: June 2004: IA Development System Available July 2004: Delivery of first version of Stand-Alone IA |
| Notes: It is expected that IA is normally delivered as a system to be installed on machines at the developer’s site and operated in a stand-alone mode. A central IA Development System (HCSS + IA) will be installed to allow testing of ICC IA activities and will allow remote access to data products by developers. It will also provide for external developers remote retrieval and storage of data products. This WP include any development of the HCSS Access Control System and the HCSS Sandbox environment necessary to control developers access to the HCSS |
| Resources: |

| WP Title: IA Access Tools | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: Provision of a set of tools to allow IA processing steps developers access to data products. |
| Start Date: | End Date: | Type: |
| Inputs: |
| Activities: Provision of software to allow reading and writing of data products from/to files (to include FITS format files) by IA Provision of software to allow local retrieval/storage of data products on an HCSS system (the central IA Development System) from IA Provision of software to allow remote retrieval/storage of data products on an HCSS system (the central IA Development System) from IA Participation in Software Development Team (ISDT) Meetings |
| Outputs: ‘Import/Export Data Product’ software ‘Local Data Access’ Software ‘Remote Data Access’ software |
| Assumptions: |
| Milestones: July 2004: Delivery of ‘Import/Export Data Product’ software July 2004: Delivery of ‘Local Data Access’ Software January 2005: Delivery of ‘Remote Data Access’ software |
| Notes: |
| Resources: |

| WP Title: Engineering Data | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: Provision of IA processing steps to extract raw data from the database, convert into engineering units and format as Engineering (Level 1) Data Products. These processing steps should deal with data from Detectors, PCAL, SCAL, SMEC, S/C, Housekeeping and BSM and convert from ADC values into voltage, current etc. |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Definition of Spacecraft pointing data TM data (ingested into the HCSS) containing data of each type Conversion information from instrument manufacturer Test data from ground testing Simulated/test spacecraft data |
| Activities: Define Level 1 Data products for each type of data (in coordination with other users of the data) Provide software modules to convert raw data into engineering units for each type of data Provide software modules to convert input conversion information and/or test data into conversion tables Prepare conversion table from input data from instrument manufacturers and testing for each instrument model Generation of test data products Participation in OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Conversion tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: January 2005: Delivery of Processing Modules for Detector, PCAL, BSM, Housekeeping data TBD: Delivery Spacecraft (pointing) Data definition TBD: Delivery of Processing Module for Spacecraft (pointing) Data |
| Notes: |
| Resources: |

| WP Title: Detector Response | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: Provision of IA processing steps to correct for the relative response of detectors as measured using the PCAL during observations and applying an absolute responsivity correction determined by separate calibration observations. |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information for absolute calibration TM data (ingested into the HCSS) containing test PCAL data Processed test detector and PCAL data products |
| Activities: Define input data products for detector and PCAL data (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Define a method of using PCAL for relative response determination Define relative responsivity calibration files Define absolute responsivity calibration files Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provide software to generate calibration files from input instrument information Provide software modules to determine the relative detector response from PCAL operations and to apply this to detector data. Provide software modules to determine the absolute responsivity correction and to apply this to detector data Define Quality Control data products for monitoring observation quality Provide software modules for deriving Quality Control data products Define long term trend data products for monitoring detector response Provide software modules for deriving long term trend data products for monitoring detector response Participation in OBST, CALT and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Calibration Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: It is TBD whether this WP should also cover use of SCAL to monitor spectrometer detector response |
| Resources: |

| WP Title: BSM | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage deals with the handling of BSM data processing |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information for BSM pointing determination TM data (ingested into the HCSS) containing test BSM data Processed test detector |
| Activities: Define input data products for detector and BSM data (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Define BSM pointing calibration files Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provide software module(s) to determine the relative pointing position from the BSM data Provide software module(s) to use the relative and absolute pointing position to demodulate the chopped data Provide software to generate calibration files from input instrument information Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring BSM operation Provide software modules for deriving long term trend data products for monitoring BSM operation Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Calibration Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Averaging | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage covers the data processing for averaging detector data.This will involve taking into account the absolute position of the pixels on the sky. Included in this WP is some form of statistical analysis to remove outlying data values (deglitching) |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Processed test detector data products |
| Activities: Define input data products for detector data (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Provide software module(s) to spatially average the detector data and identify and removing (TBC) ‘glitched ‘ data using the absolute pointing position of each pixel Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring detector glitches Provide software modules for deriving long term trend data products for monitoring detector glitches Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Deglitching | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage covers those data processing steps used to identify and remove (or flag for removal, TBC) detector data that is affected by ‘glitches’ – assumed to be caused by cosmic ray hit son the detector |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Processed test detector data products |
| Activities: Define input data products for detector data (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Provide software module(s) to identify and removing (TBC) ‘glitched ‘ data Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring detector glitches Provide software modules for deriving long term trend data products for monitoring detector glitches Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Pointing | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage covers data processing steps, which use spacecraft pointing data to correct for telescope pointing drift and to reconstruct the absolute pointing during an observation It also covers handling the Nodding mode of the telescope and flagging telescope turn around periods during scan mapping |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Processed test detector and S/C data products |
| Activities: Define input data products for detector and S/C data (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Define pointing calibration files Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provide software module(s) to assign s/c pointing information to the detector data, correcting for telescope pointing drift, reconstructing the absolute pointing, assigning nodding information and flagging telescope turnaround periods. Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define TBD long term trend data products for monitoring BSM operation Provide TBD software modules for deriving long term trend data products for monitoring BSM operation Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Flat Fielding | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage covers data processing steps to remove the different sensitivity of pixels in the SPIRE arrays. This workpackage initially also includes corrections for optical and electrical crosstalk between pixels, although this may have to be taken care of elsewhere. |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information for flat fielding and crosstalk removal Processed test detector data products |
| Activities: Define input data products (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Define calibration files for flat fielding and electrical and optical crosstalk removal Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provide software module(s) to correct for electrical and optical crosstalk between pixels Provide software module(s) to flat field the detector data Provide software to generate calibration files from input instrument information Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring flat fielding Provide software modules for deriving long term trend data products for monitoring flat fielding Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Calibration Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Fourier Transformation | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage covers processing steps to convert photometrically corrected detector data timeline into a spectrum using converted SMEC Data. This involves assigning an Optical Path Difference to each detector sample, interpolating into an equally sample dataset (TBC), phase correction and Fourier transformation. |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information to convert from SMEC encoder position to Optical Path Difference TM data (ingested into the HCSS) containing test SMEC data Processed test detector and SMEC data products |
| Activities: Define input data products for detector and SMEC data (in coordination with other users of the data) Define output data products for spectra (in coordination with other users of the data) Define SMEC calibration files Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provision of software modules to convert SMEC positional data to Optical Path Difference Provision of software modules to regrid detector data, extract, phase correct and transform interferograms into spectra Provide software to generate conversion table/curves from input data from instrument manufactures and testing Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring SMEC operation Provide software modules for deriving long term trend data products for monitoring SMEC operation Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Conversion Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: SCAL | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: SCAL provides a continuous signal into the second port of the FTS. The resultant interferogram reflects the difference between this signal and the input signal. This deal with data processing to correct for variations in the SCAL signal with time and its spectral content |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information to convert from SCAL housekeeping to signal and spectrum onto detectors TM data (ingested into the HCSS) containing test SCAL data Processed test detector and SCAL data products |
| Activities: Define input data products for detector and SCAL data (in coordination with other users of the data) Define output data products for detector (in coordination with other users of the data) Define TBD SCAL calibration files Check Calibration Plan provides required TBD calibration files Analysis of data from TBD Calibration Tests Provision of software modules to convert SCAL housekeeping data to signal/spectrum on to detectors Provision of software module(s) to correct detector signal levels for time variation of signal from SCAL Provision of software module(s) to remove for spectral input signal from SCAL from detector signals Preparation of Conversion table/curves from input data from instrument manufactures and testing Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring SCAL operation Provide software modules for deriving long term trend data products for monitoring SCAL operation Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Conversion Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Telescope | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage deals with data processing to correct for variation in the input signal due to drifts in the telescope background and removal of telescope emission from spectra |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information to convert from S/C housekeeping to signal and spectrum from the telescope TM data (ingested into the HCSS) containing test S/C data Processed test detector and simulated S/C data products |
| Activities: Define input data products for detector and S/C data (in coordination with other users of the data) Define output data products for detector (in coordination with other users of the data) Define telscope calibration files Check Calibration Plan provides required calibration files Analysis of data from TBD Calibration Tests Provision of software modules to convert S/C housekeeping data to signal/spectrum on to detectors Provision of software module(s) to correct detector signal levels for time variation of signal from telescope Provision of software module(s) to remove for spectral input signal from telescope from detector signals Preparation of Conversion table/curves from input data from instrument manufactures and testing Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring telescope signal Provide software modules for deriving long term trend data products for monitoring telescope signal Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Conversion Data/Tables for S/C |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Spectral Response | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage deals with data processing to correct for the spectral response of the instrument |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Calibration information to correct fro the instrument spectral response Processed test detector data products |
| Activities: Define input data products for detector data (in coordination with other users of the data) Define output data products for detector data (in coordination with other users of the data) Define calibration files Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provision of software module(s) to correct for the instrument spectral response (it is TBD if this will need to take into account time variations in spectral response) Preparation of Conversion table/curves from input data from instrument manufacturers and testing Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring spectral response variations Provide software modules for deriving long term trend data products for monitoring spectral response variations Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Conversion Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: User Products | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: This workpackage deals with data processing to reduce into a form suitable for use by observers for scientific analysis. This completes the generation of minimal SPIRE Data Products. The currently identified processing includes: Averaging Spectra Flux conversion to Watts Colour correction (TBC) Flux conversion to Janskys (TBC) Determination of source signal and position from Jiggle observations |
| Start Date: | End Date: | Type: |
| Inputs: IA Development System Definition of Output Data products Processed test detector data products |
| Activities: Define input data products (in coordination with other users of the data) Define required calibration files Check Calibration Plan provides required calibration files Analysis of data from Calibration Tests Provision of software module(s) to reduce the detector data into the form required Preparation of Conversion table/curves from input data from instrument manufacturers and testing Define TBD Quality Control data products for monitoring observation quality Provide TBD software modules for deriving Quality Control data products Define long term trend data products for monitoring jiggle operations Provide software modules for deriving long term trend data products for monitoring jiggle operations Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Processing modules Conversion Data/Tables for each instrument model |
| Assumptions: This software will be written in Java/Jython to run inside the IA framework |
| Milestones: July 2004: Definition of Data Products January 2005: Delivery of Processing Modules January 2005: Delivery of Conversion Data/Tables |
| Notes: |
| Resources: |

| WP Title: Scan Mapping | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: Full analysis of scan-map data to produce final maps, noise estimates and source extraction will be complex and specialised. This observing mode is expected to be used for large spatial survey programmes carried out by large consortia with relevant expertise, and bringing to the project additional data-processing capabilities over and above what the ICC will provide. This WP covers the tasks needed to coordinate the provision of this software from external users and define the input data products to be supplied |
| Start Date: | End Date: | Type: |
| Inputs: |
| Activities: Definition of input Data Products (in coordination with other users of the data) Coordination of Development activities Organisation of Meetings Participation in CALT, OBST and ISDT Meetings |
| Outputs: Data Product Definitions Data processing software Minutes of meetings |
| Assumptions: |
| Milestones: |
| Notes: |
| Resources: |

| WP Title: Quality Control ‘Pipeline’ | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: The HSC will pass each observation through a standard set of processing steps (pipeline), which should produce an output that allows an assessment of the quality of the data obtained with that observation. Data Processing workpackages include activities to provide quality data at each step of the data processing. This workpackage covers the specification and provision of any additional processing required to provide Quality information and the generation of a Quality Control ‘pipeline’ for use by the HSC |
| Start Date: | End Date: | Type: |
| Inputs: Specification of the SPIRE Observation modes |
| Activities: Definition of QCP output products (in coordination with HSC) Development of additional data processing steps, as required Preparation and test of the QCP pipeline |
| Outputs: Data Product Definitions Processing modules QCP pipeline |
| Assumptions: It is assumed that the majority of the processing steps will already be present as part of the standard processing pipeline additional software may be needed to consolidate the information already present in the data products (errors etc) and to perform processing to look for specific problems. |
| Milestones: |
| Notes: |
| Resources: |

| WP Title: Photometric Data Analysis | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: It is currently planned that the ICC standard processing will stop with the reduction and calibration of the detector data. There is no intention to co-add images to produce maps or to identify sources in these. It is expected that the data can be imported into existing data analysis packages to provide this functionality. Phase 1 of this work package covers the investigation of available data analysis packages (e.g. SURF) and production of a report on their suitability, both from a functional point of view, and our ability to include it as part of the Herschel Interactive Analysis distribution package (including cost to Herschel and the users) Phase 2 of this work package, if appropriate, covers the development of the interface to a selected package. |
| Start Date: | End Date: | Type: |
| Inputs: Phase 2: Processed test IA data products |
| Activities: Phase 1: Define the Functional Requirements of the additional package Evaluate available packages Provide a report on their suitability Phase 2: Development of interface(s) to the package, including testing with data Participation in Software Development Team (ISDT) Meetings |
| Outputs: Phase 1: Report on Suitability of Data Analysis packages Phase 2: Processing modules to interface to package |
| Assumptions: |
| Milestones: |
| Notes: PACS are providing such an analysis package themselves and would like to discuss its use for SPIRE data. A joint development may be a possible alternative to be considered (though the effort available may preclude this) It remains to be seen if phase 2 of this workpackage can be accommodated in the ICC budget |
| Resources: |

| WP Title: Spectrometric Data Analysis | WP Number |  |
| --- | --- | --- |
|  | Version: | 1.0 |
| WP Manager: | Date: | 24 Sep 03 |
| Description: It is currently planned that the ICC standard processing for spectral observations will stop with the reduction and calibration of the detector data into individual spectra. There is no intention to, for example, co-add spectra or to identify lines within these. It is expected that the data can be imported into existing data analysis packages to provide this functionality. Phase 1 of this work package covers the investigation of available data analysis packages and production of a report on their suitability, both from a functional point of view, and our ability to include it as part of the Herschel Interactive Analysis distribution package (including cost to Herschel and the users) Phase 2 of this work package, if appropriate, covers the development of the interface to a selected package. |
| Start Date: | End Date: | Type: |
| Inputs: Phase 1: Define the Functional Requirements of the additional package Evaluate available packages Provide a report on their suitability Phase 2: Development of interface(s) to the package, including testing with data Participation in Software Development Team (ISDT) Meetings |
| Activities: Phase 1: Report on Suitability of Data Analysis packages Phase 2: Processing modules to interface to package |
| Outputs: Phase 1: Report on Suitability of Data Analysis packages Phase 2: Processing modules to interface to package Participation in Software Development Team (ISDT) Meetings |
| Assumptions: |
| Milestones: |
| Notes: PACS are providing such an analysis package themselves and would like to discuss its use for SPIRE data. A joint development may be a possible alternative to be considered (though the effort available may preclude this) It remains to be seen if phase 2 of this workpackage can be accommodated in the ICC budget |
| Resources: |

| GHS4 | ICC Operations Phase |
| --- | --- |

| GFS41 | ICC Operations Continuous Tasks |
| --- | --- |
| GHS41X1000 | Operations Management |
| GHS41X2000 | Project Office |
| GHS41X3000 | Product/Quality Assurance |
| GHS41X4000 | Support to Consortium |
| GHS41X5000 | Recurrent Costs |

| GHS42 | Routine Operations Activities |
| --- | --- |
| GHS42X1000 | Monitor Instrument Health |
| GHS42X2000 | Calibration Processing |
| GHS42X3000 | Performance Monitoring |
| GHS42X4000 | Trend Analysis |
| GHS42X5000 | Quality Control |
| GHS42X6000 | HelpDesk |
| GHS42X7000 | Information dissemination |
| GHS42X8000 | Generate Calibration Observations |
| GHS42X9000 | Scheduling Observations |

| GHS43 | Non-Routine Activities |
| --- | --- |
| GHS43X1000 | Performance verification |
| GHS43X2000 | Key Programmes |
| GHS43X3000 | Problem Handling |
| GHS43X4000 | Calibration Evolution |
| GHS43X5000 | Use of Test Facilities |

| GHS44 | Software Evolution |
| --- | --- |
| GHS44X1000 | IA Framework Evolution |
| GHS44X2000 | Data Processing Modules evolution |
| 44X2100 | Implement New/Updated Modules |
| 44X2200 | Science Verification |
| GHS44X3000 | Calibration Analysis Modules Evolution |
| GHS44X4000 | Trend Analysis Modules Evolution |

| GHS45 | Software Maintenance |
| --- | --- |
| GHS45X1000 | SPIRE Contribution to HCSS S/W Maintenance |
| GHS45X2000 | Interactive Analysis Framework and Modules Maintenance |
| GHS45X3000 | Software Infrastructure Maintenance |
| GHS45X4000 | Other ICC Software Maintenance |