| Spacecraft / Project | Herschel / SPIRE |
| --- | --- |
| Instrument / Model | PFM 1 |
| Sub System / Serial No. | NA |

| Type of Test | Cold functional and performance test |
| --- | --- |
| AIV Facility Test No. | NA |
| Location & Date(s) of Testing | From 14/1/05 |
| Applicable Test Specification (Document No. & Issue) | Test Plan SPIRE-RAL-DOC-2055 issue 1 |
| Applicable Test Procedure (Document No. & Issue) | SPIRE-RAL-PRC-02223 issue 0.2 |
| AIV Facility Test Plan (if applicable?) | NA |

| Documentation / Inspection Status |
| --- |
| As Built Status? | To be completed |
| List of all items /Parts |  |
| Special Instructions |  |
| Inspection Status and Records: |
| Hazards Identified | Ref SPIRE risk assessment ESD precautions to be observed. ESD |
| Cleanliness | Inspected in G56 Test facility to be class 6 (old 1000) to be tested before FPU integration |
| Unit/Item Bagged | NA |
| Screws Locked | NA |
| Connector Savers | To be agreed |
| Other |  |

| Assignment of Personnel |
| --- |
| Function | Name | Contact number |
| Test Director | Dave Smith |  |
| Project Manager | Eric Sawyer |  |
| AIV Facility Manager | Dave Smith |  |
| Safety Officer | Dave Smith |  |
| Product Assurance | Eric Clark |  |

CONTINUATION SHEET

| As Built Status (Will the following have an Impact on the test performance / results?) |
| --- |
| Review of all “NCR’s” |  |
| Review of all “Waiver’s” |  |
| “Open Work” | Facility: Electrical safety checks Fit mass spec External heaters Issue performance test procedure and master procedure Harness integration procedure to be updated QLA update See FPU status |
| Other |  |
| MIP’s or KIP’s | KIP final inspection of FPU, 17/1/05 MIP before closing tank, final TRR 27/1/05 |

ACTIONS / COMMENTS / OBSERVATIONS: Facility NCRs 0084, heaters failed, now repaired. 0085, turbo pump failure, use as is. Monitor during test 0086, cryostat thermometers failure, repaired wires. Helium leak, mass will be fitted to monitor helium. FPU status Open work. JFETS, test and fit. Fit Detector harness Fit PTC Fit BSM Remove mirror covers Final inspection Fit instrument covers Fit to HOB Connect JFETS Electrical check Fit thermal straps Alignment cubes Hob frame MGSE. Bag and move to cryolab Bruce to check the LASER MCU and mechanism status Test status, the following tests have been completed. Interface check Inrush current No telemetry due to EGSE problem Command to 060 (PFM now FS) Motor coil parameter -1 or +1 is causing some confusion. Software change (MCU) may be required. Sensor on redundant Jiggle has low sensitivity. Now repeat tests on 070 Test with cryostat harness. Tests with DPU outstanding, these need to be done at latest during warm functional test. Warm testing can be done open loop if software update is required and not available. EIDP required for 070. Calibration data to be sent from ATC. Didier to return to RAL for further tests. Non linear control system will not be implemented. SMEC commanding scenario to be discussed. Warm units and OBS status. MCU is now separate. All warm units to be grounded. More earth straps required. Test on MCU, DCU, DPU to be powered up from Power Bench. Updated OBS received, and some tests completed. Essential to do WFT using FPU simulator. QLA update complete, testing required. HCSS acceptance tests outstanding. To be done before WFT. NOTE Launch latch not to be operated cold BSM not to be used in closed loop before software update These features to be included in the main test procedure. All test procedures to be signed off by interested parties. Flash, chop and jiggle map command lists have been written. SCAL control, outstanding. Two PIDs parameter required after tests. PTC, PID parameters and procedure needed by Ken. Doug has written a note on this. Temperature data should be copied across to the HK. This needs to be checked. Cooler recycle to be written as command script. Cooler procedure to be checked. Mode switching. CUS scripts are available. Master test procedure, Dave needs comments back. Cold functional test to follow Samuels test plan Mechanism test to be done before detectors tests, mechanisms need to be in home positions. Detailed mechanism detailed test plan is still required. Bruce will discuss with Didier. SCAL, PCAL. Pete required. Action on Pete to review the test procedure for PCAL and SCAL, warm functional test. Alignment procedure. Yes existing Cold test procedures. Needs updating, all inputs received, some SMEC input needs refining. No redundancy testing, warm electronics will not support this Observation test not yet defined. Needs discussion between Ken and Dave Clements. Scripts status BDAs done, SCAL almost done. PCAL almost done. BSM and SMEC still need some work.

Basic operating procedures to be tidied up. Hard copies to be provided, Dave to do. Phase two of TRR to be held on 27/1/05 17/1/05 Continuation of TRR with JPL Eric Bruce Marty Pegg Jamie Dave Carsten Eric C NCRs Helium leak will be monitored using a mass spec. Pumping will be continuous. Switch on and running procedure. Concern about cooler heater is not founded and we will see if this happens. Vss first then Vdd Off Vdd first and then Vss Heater procedure, start at 2v and do not exceed 3v. (2v is thought to be sufficient to turn on the JFETS) Time constant is 20sec. Failure modes doc to be sent to RAL from JPL in a few days. Test to switch on LIAs is now planned for Friday, also test for voltage transient when DCU is powered on. QM1 electronics will be used, no test equipment for DC load curves. Grounding will be checked and tidied up Do power cycles of JFETS have to be minimized? i.e. optimize the power cycles. Yes we will do that. Function test 7/2/05. first power up of JFETS. (earliest) Tests at JPL need to mimic the tested and approved switch on procedure. First switch on shall only happen when detectors are cold, existing order satisfies this restriction. Amend procedure to make this a condition. Remove DCU 06 from procedure. JPL to review test procedure.

| Decision for test continuation: | YES / NO / REVIEW | Review Date: | 27/1/05 |
| --- | --- | --- | --- |
| Company | Name |  |
| ESTEC | Carsten Scharmberg Phone |  |
| LAM | Dominique Pouliquen Phone Didier Ferrand |  |
| RAL | Eric Sawyer Dave Smith Ken King Bruce Swinyard | Tanya Lim Doug Griffin Samuel Sunil Sider |
| Cardiff | Tim Waskett Pete hargrave |  |
| IC | Davide Rizzo |  |
| ATC | Phil Parr-Burnham Brian Stobie |  |