SPIRE

| SUBJECT: | Cold workmanship vibration test procedure PFM |
| --- | --- |
| PREPARED BY: | E Sawyer |
| DOCUMENT No: | SPIRE-RAL-PRC-002598 |
| ISSUE: | 1 | Date: | 5/4/06 |
| CHECKED BY: | …………………………………. | Date: | …………………………. |
| APPROVED BY: | …………………………………. | Date: | …………………………. |

Distribution

# Change Record

| ISSUE | DATE |  |
| --- | --- | --- |
| 1 | 5/4/06 | New issue |

# Table of Contents

1.	SCOPE	7

2.	Accelerometer allocation	7

3.	Temperature sensor locations	7

4.	Step by step test sequence record	8

# Glossary

| SPIRE | Spectral and Photometric Imaging REceiver |
| --- | --- |

# References

# Applicable Documents

| No | Document | Ref |
| --- | --- | --- |
| AD1 | SPIRE PFM cold vibration test plan | SPIRE-RAL-PRC-002524 |

Reference Documents

# SCOPE

This document describes the detailed procedure to be followed during the cold vibration testing on the FPU to be carried out at CSL, Liege.

It should be used in conjunction with AD1

# Accelerometer allocation

| Channel No | Location | Type | Serial no | Code | Axis | Feed thro’ |
| --- | --- | --- | --- | --- | --- | --- |
|  | FPU top of optics bench over cone | 7724 |  | FPUX | X | 4 |
|  | FPU top | 7724 |  | FPUY | Y | 5 |
|  | FPU top | 7724 |  | FPUZ | Z | 6 |

# Temperature sensor locations

| Sensor No | Location | CODE | Calibration Curve Prime | Calibration curve Redundant |
| --- | --- | --- | --- | --- |
| 1 | RF filter | RF | X30977 | X31056 |
| 2 | Spectrometer 2K | SPEC | X29606 | X29592 |
| 3 | Photometer 2K | PHOT | X29601 | X29603 |
| 4 | Optical sub bench | OPSB | X30981 | X29602 |
| 5 | Input baffle | BAF | X29604 | X31033 |
| 6 | BSM/SOB interface | BSM | X29597 | X31036 |

NB the redundant set will be used for this test

# Step by step test sequence record

| No | Activity | Time | Date | Run number | Comments | Resp. |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Test preparation |  |  |  |  |  |
| 1.1 | Unpacking from container: As per AD1 Store container until the end of the test | 3 hrs | 8/5/06 |  |  |  |
| 1.2 | Visual inspection of the FPU Cover with cover provided while awaiting integration Fit the three accelerometers to the FPU. | 2 hrs 1 hr | 8/5/06 |  | Record any anomalies |  |
| 2 | Vibration Test in X axis |  |  |  |  |  |
| 2.1 | Test preparation Assuming test adaptor is fitted to the shaker Fit FPU to test adaptor in accordance with AD1 Check torque of mounting feet 8.1 Nm plus running torque for M6 8.25 plus running torque or M8 Kaylock nut. 2.1 Nm for the JFET bolts. Remove MGSE Fit temporary thermal straps between FPU and fixture, 4 straps at each end of the SOB. Cover detector harness connectors with copper tape to provide ESD protection Check isolation and record results L1 to FPU FPU to fixture Spectrometer L0 to FPU Pump L0 to FPU Evaporator L0 to FPU Note JFET supports to be lifted from the fixture for this test Connect accelerometers carry out continuity check. Carry out very low level test in ambient 0.25g 5 to 2000Hz Note The Kevlar suspended detectors will not tolerate significant levels when warm. This test is to verify the instrumentation only. Connect temperature sensors Note These sensors do not record accurate temperatures at room temperature. Accurate only below 40K. Individual calibration curves will be supplied by SPIRE | 3 hrs ½ hrs ½ hrs 2 hrs ½ hrs | 8/5/06 |  |  |  |
| 3 | TRR | 4 hrs | 9/5/06 |  |  |  |
| 4 | Shrouds installation, connection of pumps and fluid lines | 2 days | 9/5/06 10/5/06 |  |  |  |
| 5 | Evacuation Monitor pressure during evacuation and check for consistence with evacuation rate requirement in AD1 Evacuation and re-pressurisation to be in accordance with AD1, max rate 50mb/min Note pressure values or attach record |  | 11/5/06 |  |  |  |
| 6 | Cool down Monitor temperature sensors during cool down and check for consistence with cool down requirements in AD1 Max rate of change of BSM sensor is:- Ambient to 200K -- 5K/hour 200K to 100K -- 10K/hour Below 100K -- 50K/hour Maximum delta T between BSM and LTA is:- Ambient to 200K -- 35K 200K to 100K -- 40K. Below 100K, No restriction Note Temperature or attach temperature record of temperature sensors |  | 11/5/06 12/5/06 13/5/06 14/5/06 |  |  |  |
| 20.1 | Resonance search Check results against those expected. Confirm levels for next test | 1/2hr 1hr 1hr | 15/5/06 |  | 0.25g 5 to 2000Hz |  |
| 20.5 | Low level Random test test to AD1 at –12dB Check results | 1/2hr 1/2hr |  |  | -12dB Full level is Frequency Range Hz Acceptance levels 20-100 +3dB/Oct 100-150 0.032 g2/Hz 150-300 0.0128 g2/Hz 300-2000 -12 dB/Oct Global 2.77 g RMS |  |
| 20.6 | Intermediate level Random test test to AD1 at –6dB Check results | 1/2hr 1/2hr | 15/5/06 |  | -6 dB Full level is Frequency Range Hz Acceptance levels 20-100 +3dB/Oct 100-150 0.032 g2/Hz 150-300 0.0128 g2/Hz 300-2000 -12 dB/Oct Global 2.77 g RMS |  |
| 20.7 | Acceptance level random test Carry out test to AD1 Check results | 1/2hr 1/2hr | 15/5/06 |  | Full level Frequency Range Hz Acceptance levels 20-100 +3dB/Oct 100-150 0.032 g2/Hz 150-300 0.0128 g2/Hz 300-2000 -12 dB/Oct Global 2.77 g RMS |  |
| 20.8 | Resonance search Carry out resonance search as before Compare with previous results | 1/2hr 1/2hr | 15/5/06 |  | 0.25g 5 to 2000Hz |  |
| 20.9 | Post test analysis Check completeness of data Carry out initial assessment | 1/2hr 2hrs |  |  |  |  |
| 21 | TRR |  |  |  |  |  |
| 22 | Post Test Activities • check completeness of test data • Warm up Monitor temperature sensor during warm up and check for consistence with cool down requirements in AD1 Note Temperature or attach temperature record of temperature sensors Max rate of change of BSM sensor is:- Ambient to 200K -- 5K/hour 200K to 100K -- 10K/hour Below 100K -- 50K/hour Maximum delta T between BSM and LTA is:- Ambient to 200K -- 35K 200K to 100K -- 40K. Below 100K, No restriction Venting Monitor pressure during venting and check for consistence with evacuation rate requirement in AD1 Note pressure values or attach record Max rate 50mb/min | 4hrs | 16/5/06 17/5/06 18/5/06 19/5/06 |  |  |  |
| 23 | Dismount dismounting of shrouds • Visual inspection of test specimen • Removal of instrument (TBC) and cleanliness inspection with UV light • Installation of the instrument inside its own container in accordance with AD1 | 4hrs 1hr 2hr 2hr | 20/5/06 |  |  |  |
| 24 | Transport |  | 21/5/06 |  |  |  |

Annex 1   PFM build standard