| Spacecraft / Project | Herschel / SPIRE |
| --- | --- |
| Instrument / Model | PFM |
| Sub System / Serial No. | N/A |

| Type of Test | PFM-5 Cold Test Campaign |
| --- | --- |
| AIV Facility Test No. | N/A |
| Location & Date(s) of Testing | SPIRE Test Facility |
| Applicable Test Specification (Document No. & Issue) | SPIRE-RAL-DOC-002535 – Issue 2.0 |
| Applicable Test Procedure (Document No. & Issue) | SPIRE-RAL-PRC-002816 – Issue 1.0 |
| AIV Facility Test Plan (if applicable?) | N/A |

| Documentation / Inspection Status |
| --- |
| As Built Status? | Currently at issue 2.8 – Numbers of JFET modules to be updated. Entrance aperture cover fitted & SMEC prime and redundant harness swapped |
| List of all items /Parts |  |
| Special Instructions |  |
| Inspection Status and Records: |
| Hazards Identified | Ref SPIRE risk assessment ESD precautions to be observed – only trained personnel to access lab. ESD |
| Cleanliness | Inspected in G56 Test facility to be class 6 (old 1000) |
| Unit/Item Bagged | N/A |
| Screws Locked | N/A |
| Connector Savers | Are being used on FPU and Warm Units |
| Other | Adaptors fitted to MCU P17 & P18 to correct error in warm test harness. |

| Assignment of Personnel |
| --- |
| Function | Name | Contact number |
| Test Director | Dave Smith | Ext 5996 |
| Project Manager | Eric Sawyer | Ext 5385 |
| AIV Facility Manager | Dave Smith | Ext 5996 |
| Safety Officer | Dave Smith | Ext 5996 |
| Product Assurance | Eric Clark | Ext 5662 |

CONTINUATION SHEET

| As Built Status (Will the following have an Impact on the test performance / results?) |
| --- |
| Review of all “NCR’s” | NRB held on 31st Jan 2007 – ref SPIRE-RAL-MOM-002818. No open NCRs affecting this test campaign. |
| Review of all “Waiver’s” | None applicable |
| “Open Work” | See below |
| Other |  |
| MIP’s or KIP’s | Visual inspection when cryostat opened showed hardware ok after PFM-4. |

ACTIONS / COMMENTS / OBSERVATIONS: Status SSW test – warm test performed with reworked harness - 16nVHz-1/2 Harness rework appears to fixed JFET imbalance – detector spreadsheet has been updated and will be circulated. Cryostat pumped down – LN2 shrouds filled and start to cool to 80K SMEC unlatched WFT Completed successfully. Standard and closed loop tests of SMEC were fine. OBS 2.2G tested on AVM – ok Need to test VMs – 2 changes needed – increase time between interrupts on HW VM & implement new floating point library. Should be completed on 1st February. DCRU No open work. HCSS Acceptance testing on 0.4.1 – should be completed 1st February. MIB Imported version PFM-5 2.2G1 onto SCOS with corrected SMEC temp cal tables. Scripts There are separate scripts to recycle cooler on prime and redundant. New script needed to perform load curves with PCAL flashes at each level. Tanya to raise an SCR. AOT scripts to be ingested – will be done after HCSS acceptance tests. There are 4 sets of cal tables for SMEC Prime/Redundant & Hot/Cold – to be updated. QLA V3.3 – main changes are table updates and support to dynamic changing of MCU engineering parameters. Planned shutdown of computers over weekend has affected one of the displays on the QLA machine. Under investigation.

Test Plan Test priorities – detector characterization, SMEC testing, EMC (2 days TBC). Fillippo expected 19th/20th February Dominique TBD Tanya has sent round test spreadsheet based on JPL inputs for comment – JPL proposals discussed during weekly telecom. Tanya to update test spreadsheet and distribute. JPL Availabilities Bernhard 12th Feb to 19th Feb Hien 7th Feb to 21st Feb Jamie 19th Feb to 28th Feb (TBC) Planning Cool Functional Test Friday/Monday Cool to 4K on Tuesday 6th Cold functional tests on Wednesday 7th Cold testing starts Friday 9th Start warm up on 2nd March Back to G56 on 12th March AOB FPGA running times continue to be logged – totals to be added.

Test Readiness We are ready to go.

| Decision for test continuation: | YES / NO / REVIEW | Review Date: | 31-Jan-2007 |
| --- | --- | --- | --- |
| Company | Name |  |
| RAL | Eric Sawyer Dave Smith Ken King Bruce Swinyard | Tanya Lim Doug Griffin Sunil Sider Eric Clark |
| Cardiff | Matt Griffin |  |