Scope

The aims of the SPIRE Flight Spare instrument level test programme are briefly stated and a top level description of the test programme is given.

The SPIRE Flight Spare Instrument

The FS build standard is as follows:

FPU		Flight quality for all sub-systems with the following caveats:

SMEC – no redundant side optical encoder (operation failure)

JFETs – x out 15 units are non-flight quality (attrition)

DRCU		QM2 is used – no redundancy on SCU

DPU		CFM

OBS		?

Flight Spare testing rationale

The basic purpose of the FS was to provide an FPU capable of being swapped for the PFM if there is a major problem during system level AIV.  This aim is compromised by the failure of the FS SMEC redundant side encoder and the incomplete set of flight quality JFETS.  The FS therefore provides a set of parts that can be swapped into the PFM in the event of a major failure.

The secondary aim of building the FS is to provide a test bed for the easy and rapid evaluation of on-board software upgrades; in-flight operations validation and trouble shooting of problems found on the flight unit, either during ground testing or once in flight.

The FS instrument level test campaign must therefore show that the sub-systems, as integrated into the instrument, perform as intended and are capable of being flown if necessary.  To this end the test plan outlined here provides for the basic functional and performance testing of the instrument with, initially , little detailed characterisation, as the first priority.  The second priority will be the validation of in-flight procedures and on-board software and the lowest priority is given to detailed performance characterisation.

Whether a vibration test is to be carried out on the FPU is to be decided dependent largely on schedule considerations.  This is not discussed further here except to state that the basic function and performance test will be conducted before and after any vibration campaign.

Outline Test Procedure

Functional Test

General procedure is contained in SPIRE-RAL-PRJ-001652 – specific procedures carried out before (PFM4 and PFM5) are as follows.

The standard warm functional test (SPIRE-RAL-PRC-002322) will be carried out before and after installation into the test cryostat.

The standard cool functional test (SPIRE-RAL-PRC-002584) will be carried out at LN temperature

The standard cold functional test (SPIRE-RAL-REP-002585 see also SPIRE-RAL-PRC-002398) will be carried out once the instrument reaches operational temperature

Operation and Performance Verification

In order to check the basic operation and performance of the instrument the following set of tests is mandatory:

| Proc ID | Description | Tests Used |
| --- | --- | --- |
|  | Cooler recycling | CREC |
|  | Detector noise P – basic check for gross problems – includes phasing | ILT-PERF-VSS ILT-PERF-DPH ILT-PERF-DNA |
|  | Detector noise S – basic check for gross problems – includes phasing | ILT-PERF-VSS ILT-PERF-DPH ILT-PERF-DNA |
|  | Instrument throughput P – CBB – loadcurves vs TCBB | ILT-PERF-DAB ILT-PERF-DAL |
|  | Instrument throughput S – CBB – loadcurves vs TCBB | ILT-PERF-DAB ILT-PERF-DAL |
|  | Optical alignment P – centre of field/overlapping pixels | ILT-PERF-FOC ILT-PERF-PKI ILT-PERF-PKB |
|  | Optical alignment S – centre of field/overlapping pixels | ILT-PERF-PKI ILT-PERF-PKB |
|  | BSM performance and tuning | ILT-PERF-BSM ILT-PERF-BCT |
|  | SMEC performance and tuning | ILT-PERF-SMC |
|  | Band pass P – TFTS centre of field | ILT-PERF-DSR |
|  | Band pass S – to CBB | ILT-PERF-SSC |
|  | Instrument throughput S – SCAL | ILT-PERF-DAB ILT-PERF-DAL |
|  | Band pass S – to SCAL | ILT-PERF-CSS |
|  | PCAL operation and response P | ILT-PERF-CPT ILT-PERF-CPS |
|  | PCAL operation and response S | ILT-PERF-CPT ILT-PERF-CPS |

In-flight operations validation

We wish to test that the procedures used for the commissioning, calibration and routine flight operations operate correctly when carried out with a real instrument.  In particular the upgraded on board software, which includes the Failure Detection Isolation and Recovery procedures, needs to be tested in a “live” environment in order to debug it ahead of deployment on the flight system.  The following procedures are proposed for the flight spare test campaign – some details need to be worked through.

Commissioning phase run through

AOT Testing using latest  logic

PTC tuning algorithm and in flight tuning methodology

FDIR validation and operation

Characterisation of performance

If time permits further useful tests can be carried on the FS these are aimed at providing data for testing the pipeline and characterising the instrument performance.

Long simulated observations using AOTs to provide data for pipeline testing.

Detector characteristics as function of bias frequency (gain/bias/noise dependence)

Spectrometer performance testing – checks on nulling with small area SCAL; spectral response at more wavelengths

More pixel characterisation (bandpass/psf/FoV)

Proposed schedule for performance tests

Based on the outline schedule for PFM4 – here is a possible sequence for approximately the first two of performance testing – only 8 days are shown but with single shift working and allowing for things to go wrong this will probably take 3 elapsed weeks.

| Schedule week starting # |
| --- |
| Day 1 | ID | Test description |
|  | FS-1 | Cooler recycle |
|  | FS-2 | Photometer - Phase up 130 Hz |
|  | FS-4 | Photometer dark load curve |
|  | FS-2 | Photometer standard noise test |
|  | FS-14 | Photometer PCAL level and standard flash test |
|  | FS-3 | Spectrometer - Phase up 160 Hz |
|  | FS-5 | Spectrometer dark load curve |
|  | FS-3 | Spectrometer standard noise test |
|  | FS-15 | Spectrometer PCAL level and standard flash test |
|  | FS-2 | Photometer overnight noise test |
| Day 2 |  |  |
|  | FS-6 | Photometer initial focus test using hot black body |
|  | FS-6 | Photometer peak-ups using hot black body |
|  | FS-10 | Photometer TFTS Scans |
|  | FS-2 | Photometer overnight noise test |
| Day 3 |  |  |
|  | FS-7 | Spectrometer initial focus test using hot black body |
|  | FS-7 | Spectrometer peak-ups using hot black body |
|  | FS-9 | SMEC tuning and scan checks – laser line scans SSW + SLW lines |
|  | FS-1 | Cooler recycle |
| Day 4 |  |  |
|  | FS-4 | Photometer dark loadcurve |
|  | FS-4 | Photometer loadcurves versus CBB temp (8.7,11,13,15,20 K TBC) |
|  | FS-2 | Photometer overnight noise test |
| Day 5 |  |  |
|  | FS-5 | Spectrometer dark loadcurve |
|  | FS-5 FS-11 | Spectrometer loadcurves and SMEC scans versus CBB (no SCAL) (off 8.7,11,13,15,20 K TBC) |
|  | FS-3 | Spectrometer overnight noise test |
| Day 6 |  |  |
|  | FS-1 | Cooler recycle |
|  | FS-4 | Photometer dark loadcurve |
|  | FS-4 | Photometer room loadcurve |
|  | FS-8 | BSM pixel finding |
|  | FS-8 | BSM tuning |
|  | FS-6 | Photometer beam shape using BSM |
|  | FS-2 | Photometer overnight noise test |
| Day 7 |  |  |
|  | FS-12 | Spectrometer dark loadcurve |
|  | FS-12 | SCAL-4 operation and tuning |
|  | FS-12 FS-13 | Spectrometer SCAL-4 tests load curves plus scans |
|  | FS-3 | Spectrometer overnight noise tests |
| Day 8 |  |  |
|  | FS-12 | Spectrometer dark loadcurve |
|  | FS-12 | SCAL-2 operation and tuning |
|  | FS-12 FS-13 | Spectrometer SCAL-2 tests load curves plus scans |