| PURPOSE : | CLASSIFICATION : |
| --- | --- |
| Instruments testing at S/C level |  |
| ATTENDEES | FIRM | SIGNATURE | ATTENDEES | FIRM | SIGNATURE |
| C.Scharmberg | ESA |  | G.Pilbratt | ESA |  |
| O.Bauer | PACS |  | G.Crone | ESA |  |
| H.Feuchtgruber | PACS |  | C.Jewell | ESA |  |
| P.Roelfsema | HIFI |  | F.Pedersen | ESA |  |
| P.Dieleman | HIFI |  | R.Hohn | ASED |  |
| E.Sawyer | SPIRE |  | M.Langferman | ASED |  |
| D.Montet | TAS-F |  | N.Sonn | ASED |  |
| B.Collaudin | TAS-F |  | D.Schink | ASED |  |
| A.Koppe (Part) | ASED |  | M.Priesley | TAS-F |  |
|  |  |  | S.Mooney | TASF |  |
| WRITTEN BY : | B.Collaudin |  |  |  |
| CONCLUSION : |
| DISTRIBUTION : ATTENDEES | FOR FURTHER ACTION : | ESA: L.Di Napoli, T.Passvogel TASF: Y.Roche, J.M.Reix ASED: |
|  | FOR INFORMATION : |  |
| APPROVED BY |
| NAME |  |  |  |  |
| SIGNATURE |  |  |  |  |

| CONTINUED : | ACTION |
| --- | --- |
| Agenda: Ref mail from C.Scharmberg: - Introduction and Objectives of the meeting (ESA + TASF) - Herschel S/C Acceptance campaign flow (TASF) - Project Team Organisation (TASF) - Instrument Test Matrix (TASF) - Instrument Test Constraints from S/C (TASF) - Current S/C Test Flow (TASF) - Status of Instrument verification at S/C level (TASF) - Discussion and Agreement (All) |  |
| - Introduction and Objectives of the meeting (ESA + TASF) - Herschel S/C Acceptance campaign flow (TASF) - Project Team Organisation (TASF) all 3 topics: See annex 1. Presentation from Thales. Questions: Instruments test during launch campaign = AFT (including instruments SFT) in He I is the baseline. Not possible to tilt the S/C on the launcher. Mechanical test in He I SVT1 before SPT1 because it is in He I. Transport warm means SFT warm first thing in Estec. |  |
| Instrument Test Matrix (TASF) See annex. Test duration are instrument test execution & interpretation. Not including S/C or cryostat configuration. |  |
| Current S/C Test Flow (TASF) Questions: Integration of LOU & HIFI SFT 2 (LOU SFT): 10 to 12/12/07 + Alignment on 13/12 TBC (SFT included ?) SPIRE harness correction. Before or after moving ? PACS Module 20 anomaly investigation Check point for PACS 5/12 Activity planed when ? SFT warm after S/C transportation & set up in Estec: Yes Confirmed. Transportation & set up of IEGSE. Disconnection of S/C is week 50. Instrument IEGSE pack- Week 51 Transport ahead of the S/C. Unpack & set up: Week 1 in Estec The location if IEGSE room will be distributed end of this week. Schedule: Now Instruments project managers are in the weekly distribution list of the Herschel near term schedule. NRB and scheduled tasks. NRB make recommendation to implement correction activities. The date/time of the activity has to be confirmed by AIT. Organisation: 3 shifts activities: Instrument will need to adjust to the new situation (for IST, as TV was already in 3 shifts). Instruments input are available. The complete test plan combining instruments test + satellite test + cryostat & SVM set up is not existing. . | AI 1 TASF to clarify. AI 2. TASF |
| Test Specification. Instruments teams agree with the content of the test specification 1083. Released of the signed version after review of comments in the instruments system meeting this week |  |
| TV test: Some clarification wrt TV test is needed: Clarification meeting. For instance the temperature stability, and the orientation of the S/C for cooler recycling & testing. | AI3 TASF. |
| Instruments verification |  |
| See synthesis of SFT in annex 1. |  |
| AOB: Difference of conditions between ASED-FN & ESTEC. Same AIT & PA team in FN & Estec.* |  |
| Why transporting the S/C warm to Estec Mainly Schedule reasons: Save cooling to He II & back to He I for transport |  |
| SVT – SOVT Set up of instrument will be similar to RMS Instruments will be present both in Estec & ESOC (if data are received on both places). |  |
| Delivery of procedures, scripts. Thales collects the latest issues of instrument test documentation (test procedures, scripts, reports), and make it available on the instruments ftp (ftp.hp-instruments.as-b2b.com). This documentation will be transmitted to ASED according to agreed rules. |  |
| PACS contamination and bake-out. Nothing has changed on the cryostat baking condition. It was clarified (on the baking procedures 23/5/07) before the PACS problem) that the maximum temperature that will be reached on the Instruments FPU will be <60°C. Investigation is on-going on the PACS mirror contamination. If there is a reason to change something from the PACS contamination investigation, instruments will be involved in the decision. |  |
| End of Meeting |  |

| ACTIONS | DATE |
| --- | --- |
| Origin | N° | Status | Description | Responsible | Due |
|  | 1 | Open / Close |  |  |  |
|  | 2 |  |  |  |  |
|  | 3 |  |  |  |  |
|  | 4 |  |  |  |  |
|  | 5 |  |  |  |  |
|  | 6 |  |  |  |  |
|  | 7 |  |  |  |  |
|  | 8 |  |  |  |  |

Annexes