## Risks_June_2008
| 13 June 2008 | [8 empty] | Page 1 of 3
Herschel-SPIRE UK Project: Risk Analysis
Note: This summary is based on the format specified in PPARC PROJECT Handbook, V1.1, Feb. 2005, with the following adaptations:
(i) The "Current Controls" column is not included (regarded as N/A)
(ii) The definitions of the different impact categories have been modified to make them more relevant to this project.
Likelihood (L) |  |  |  | Impact (I) | [5 empty] | L x I
1 | Rare - probability < 0.1 |  |  | 1 | Insignificant - negligible or small impact on operations, science, or costs |  |  |  |  | 1-2 Low risk
2 | Possible - probability 0.2 - 0.5 |  |  | 2 | Moderate - e.g., some loss of science; delays or inefficiency; some cost increase |  |  |  |  | 3-8 Medium risk
3 | Likely - probability 0.5 - 0.9 |  |  | 3 | Major - severe loss of science capability or efficiency and/or large cost increase |  |  |  |  | >8 High risk
4 | Very likely - probability > 0.9 |  |  | 4 | Catastrophic - loss of SPIRE instrument
| 13 June 2008 |  |  | Herschel-SPIRE UK Project: Risk Analysis | [5 empty] | Page 2 of 3
| WP | Risk description | Effect |  | Risk Score |  | Category | Mitigation action | Owner | Review point
|  |  |  | L | I | L x I
| AIV | Susceptibility of detectors to RFI in flight | Loss of sensitivity due to increased detector noise | 1 | 3 | 3 | M | Spacecraft RE tests show very low emission levels. RS tests planned in SPT. Additional shielding of SVM is the only plausible mitigation action. | SPIRE Project + JPL | SPT (July/Aug 2008)
|  | Failure of SMEC launch latch | Possible damage to SMEC during vibration qualification or launch | 1 | 3 | 3 | M | Latch power unit is designed to secure the latch during the test and launch. Has been used in qual. tests with no indication of a problem | SPIRE Project + LAM/CNES | SMEC horiz. test before SPT
|  | SMEC friction | Possible impairment of SMEC performance and/or reliability in flight | 2 | 2 | 4 | M | Assessment of data from spacecraft horiz. Test to be repeated/completed after mechanical qualification | SPIRE Project + LAM/CNES | SMEC horiz. test before SPT
|  | Detector temperatures | Loss of sensitivity if DT between cooler and arrays increases further | 2 | 2 | 4 | M | None | SPIRE Project | SPT (July/Aug 2008) - will provide direct measurement of achieved temperatures
|  | Failure of a BDA kevlar support | Thermal short between 2 K and 300 mK - likely loss of SPIRE | 1 | 4 | 4 | M | Pre-launch: warm-up and replacement of BDA. Would involve ~ 6 month delay to H-P launch. Post-launch: loss of SPIRE | SPIRE Project + JPL | SPT (July/Aug 2008)
|  | Strong SMEC susceptibility to microvibrations | Degraded SMEC performance | 1 | 3 | 3 | M | Susceptibility tests to be carried out after mechanical qual. Test; change SMEC control parameters; modification to reaction wheel operations | SPIRE Project + LAM/CNES | SPT (July/Aug 2008)
|  | Detector susceptibility to microvibrations | Degraded detector performance | 1 | 3 | 3 | M | Adjust bias frequency; modify reaction wheel operations | SPIRE Project + JPL | SPT (July/Aug 2008)
|  | Technical problems with PACS or HIFI | Launch delay and/or loss of Herschel science capability | 2 | 2 | 4 | M | N/A | Herschel Project + HIFI, PACS | Continuing
|  | Technical problems with Herschel spacecraft or with Planck | Launch delay | 2 | 2 | 4 | M | None | Herschel-Planck Project | Continuing
|  | Pressure to launch even with known instrument failures/problems | Loss of Herschel (possibly SPIRE) science capability | 3 | 3 | 9 | H | Process involving ad hoc committee of experts and stakeholders to assess situation and advise D-SRE has been defined | ESA/D-SRE | FAR
|  | Launch failure | Loss of Herschel and Planck missions | 1 | 4 | 4 | M | None by instrument teams | ESA/D-SRE | Launch
| 13 June 2008 |  |  | Herschel-SPIRE UK Project: Risk Analysis | [5 empty] | Page 3 of 3
| WP | Risk description | Effect |  | Risk Score |  | Category | Mitigation action | Owner | Review point
|  |  |  | L | I | L x I
|  | Helium leak in cryostat contaminating the detectors or cooler | Lower mission lifetime and/or degradation of detector performance | 1 | 2 | 2 | L | Getters installed in the flight cryostat. Once lid is opened in flight, it will be difficult for a leak to build up to problematic levels. Decon- tamination procedure will be tested in TB/TV. | SPIRE Project/ESA | Herschel Commissioning Phase
|  | Subsystem failure during vibration qualification | Loss of functionality | 1 | 4 | 4 | M | Warm-up and repair Would involve ~ 6 month delay to H-P launch. | SPIRE Project/ESA | Post-vibration tests (esp. SPT)
|  | Stray light in the flight environment | Science performance degradation (for SPIRE and/or PACS) | 1 | 2 | 2 | L | System analysis has been performed, but no flight-representative tests possible | SPIRE Project/ESA | PV phase
|  | SPIRE cryoharness failure during cooldown | Loss of functionality; science performance degradation | 1 | 2 | 2 | L | System verification during TB/TV which would reveal cryoharness problems | Herschel-Planck Project | TB/TV test
| ICC | Lack of readiness for launch | Inefficiency during PV; extended PV | 1 | 3 | 3 | M | Comprehensive testing and prioritisation of critical functions is planned | SPIRE Project; ICC Dev. Manager | Ground Segment Readiness Review + continuing internal monitoring
|  | Technical problems in flight (esp. but not exclusively during Commissioning/PV) | Loss of science capability and/or adaptation of operating modes | 3 | 2 | 6 | M | Some problems would not be unexpected. Part of ICC normal work will be to prioritise assessment and mitigation. FS will be available for troubleshooting and OBS update trials. | SPIRE Project; ESA | End of Commissioning Phase + end of PV Phase; routine health monitoring
|  | Inadequate resources for PV-phase workload | Delay in establishing standard operating modes | 2 | 3 | 6 | M | Staffing plan indicates adequate provision, but involves assumptions about workload, HSC effectiveness, and no major problems with HW or data systems. Active management and prioritisation will be essential. | SPIRE Project, esp. ICC Manager | GSRR + early stages of PV
|  | Inadequate ICC funding during Operations | Unable to accommodate all ICC obligations. | 1 | 3 | 3 | M | Priority would be given to up-link tasks - ensuring that observations are carried out optimally. | SPIRE Project | Continuing
|  | Loss of key ICC staff | Need to re-organise tasks; loss of effort during recruitment and training | 2 | 2 | 4 | M | Active efforts being made to ensure that all key tasks are coverable by more than one individual. Some staff turnover to be expected during the mission. | SPIRE Project | Continuing
|  | Major technical problems in flight with PACS or HIFI | Loss of PACS/HIFI science; potential increased workload on SPIRE ICC | 2 | 2 | 4 | M | No explicit allowance for this. Additional resources could be a call on UK contingency. ESA support could be sought to accommodate any additional work. | SPIRE Project/ESA | End of Commissioning Phase + end of PV Phase; routine health monitoring
|  | Pressure from ESA HSC for ICC to provide additional support for user community | Increased workload and pressure | 3 | 2 | 6 | M | Resist or seek funding assistance from ESA in the event of significant increase in scope |  | GSRR + Science Demonstrations Workshop